## Slide 1: SA WG3 Status report for FS_EDGE_Ph3
Ge Yao (China Unicom)
Bo Zhang (Huawei)

## Slide 2
TUs planned
  TU estimates and dependencies
  Total TU estimates for the study phase: 4
  Total TU estimates for the normative phase: 2
  Total TU estimates: 6
In SA3#116 meeting:
  KI on UE info verification agreed
In SA3#117 meeting:
  All KIs and solution to be proposed.
In SA3#118 meeting:
  Solution, evaluation, and its conclusion have to be achieved.
In SA3#119 meeting:
  Normative work in TS 33.501, or TS 33.558
FS_EDGE_Ph3 overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
Objective #1 | 0.5TU | 0.25 TU | No | No
Objective #2 | 1 TU | 0.25 TU | No | No
Objective #3 | 1TUs | 0.5 TU | No | No
Objective #4 | 1.5TUs | 1TU | No | No

## Slide 3
General
  TR 33.749 v0.2.0 contains scope, 1 key issue and 1 solution.
Dependencies:
  SA2 SID (TR 23.700-49: "Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3")
    Solutions available to all key issues
  SA6 WID (TS 23.558: "Architecture for enabling Edge Applications")
    Normative work is already started
Contentious Issue:
  UE info verification and its usage authorization by 5G system (need more constructive proposals)
Risks:
  None identified
FS_EDGE_Ph3 status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030036 | Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 | FS_EDGE_Ph3 | Rel-19 | S3 | December 2024 | 0% | 30% | TR 33.749

## Slide 4
Pending issues
  None
TUs consumed
  SA3#115 Adhoc-e - 0.5 TU
  SA3#116 - 0.5 TU
TUs remaining
  SA3#117 - 1 TU
  SA3#118 - 1 TU
  SA3#119 - 1 TU
Plan for completion
  SA3#119
FS_EDGE_Ph3 pending work and plan for completion