## Slide 1: SA WG3 Status report for SCAS_5G_Maint
Rong Wu, Huawei

## Slide 2
SCAS_5G_Maint overall plan
Meeting | Plans | WID TU
SA3#115 (February), finished | WID approved | 
SA3#116 (May), finished | Living CR for TS 33.117; Living CR for TS 33.514 | 0.25
SA3#117 (August) | New Living CRs for other Network Functions, e.g. TS 33.511~TS 33.530 New Living CR for TR 33.926 | 0.5
SA3#118 (October) | Last meeting for New Living CRs Convert part of living CR to normal CR, e.g. TS 33.514, TS 33.511 | 0.5
SA3#119 (November) | Convert all left living CRs to normal CR | 0.25
SA#106 (December) | Send CRs to SA for approval Plan to finalize it this year, leave more time to all other R19 SIDs/WIDs (~0.5 TU) | 

## Slide 3
General
  Potential CRs to TR 33.916, TR 33.926
  Potential CRs to TS 33.117, TS 33.511~TS 33.530, TS 33.537
Dependencies:
  NULL
Contentious Issue:
  Depending on how to improve the test cases description
Risks:
  Unclear evaluation test cases
  Lack of improvements
SCAS_5G_Maint status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030029 | Security Assurance Specification for maintenance of 5G features | SCAS_5G_Maint | Rel-19 | S3 | Dec-2024 | 15% | 0% | CRs

## Slide 4
Pending issues
  Certificate verification related test cases inclusion, etc
  Potential corrections or new security assurance requirements identified from test labs and GSMA NESASG, etc
Dependencies:
  NULL
TUs consumed
  SA3#116 – 0.25
TUs remaining
  SA3#117 – 0.5
  SA3#118 – 0.5
  SA3#119 – 0.25
Plan for completion
  SA3#119 Finalise all the CRs
  SA#106 Send TR for information and approval
SCAS_5G_Maint pending work and plan for completion