## Slide 1: SA WG3 Status report for FS_5GSAT_Ph3
Wei Zhou
CATT

## Slide 2
Meeting plan
  Meeting 1 (SA3#115 2024-02-26 2024-03-01 Athens, GR)
    TR skeleton + Key Issues
  Meeting 2 (SA3#115-adhoc-e 2024-04-15 2024-04-19 E-Meeting)
    Key Issues + Solutions
  Meeting 3 (SA3#116 2024-05-20 2024-05-24 Korea, KR)
    Solutions
  Meeting 4 (SA3#117 2024-08-19 2024-08-23 Maastricht , NL)
    Solutions + Preliminary conclusions
  Meeting 5 (SA3#118 2024-10-14 2024-10-18 India, IN)
    Solution updates + Conclusions + Preliminary WID Proposal
  Meeting 6 (SA3#119 2024-11-11 2024-11-15 Orlando , US)
    Conclusions + WID Proposal
5 TUs planned
In SA3#117 meeting:
  New solutions, solution updates, preliminary conclusion discussion
In SA3#119 meeting
  Finalize TR and propose WID
Overall plan
FS_5GSAT_Ph3 overall plan

## Slide 3
General
  TR scope has been set.
  TR architecture and security assumptions have been set.
  There are 2 key issues for Store and Forward Satellite Operation
  There is 26 solutions in the TR.
Dependencies:
  SA2’s study work on FS_5GSAT_Ph3 (TR 23.700-29)
Contentious Issue:
  None
Risks:
  None identified
FS_5GSAT_Ph3 status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020044 | Study on Security Aspects of 5G Satellite Access Phase 3 | FS_5GSAT_Ph3 | Rel-19 | S3 | November-2024 | 40% | 65% | TR 33.700-29

## Slide 4
Pending issues
  New solutions, solution updates and conclusions
Dependencies:
  Conclusions of SA2’s study work on FS_5GSAT_Ph3 (TR 23.700-29)
TUs consumed
  2 TUs used by SA3#115, SA3#115Adhoc-e and SA3#116
TUs remaining
  3 TUs for SA3#117, SA3#118 and SA3#119
Plan for completion
  SA3#119
FS_5GSAT_Ph3 pending work and plan for completion