## Slide 1: SA WG3 Status report for FS_NG_RTC_SEC_Ph2 Study on the security support for the Next Generation Real Time Communication services phase 2
Vlasios Tsiatsis, Ericsson
Xiaoting Huang, China Mobile

## Slide 2
6 TUs planned
In SA3#117 (August) meeting
  Updates of the key issues, no new key issues are expected
  Updates of existing solutions
  Potential new solution proposals
  Potential conclusions for some key issues
In SA3#118 (October) meeting
  Updates of existing solutions, few or no new solutions are expected
  Potentially more conclusions
  WID proposal for consideration, potential WID proposal agreement
SA3#119 (November) meeting
  Potential solution updates
  Final conclusions
  WID proposal agreement is expected
  Potential normative work conditionally agreed
  Draft TR 33.790 for information and approval
SA3 meetings in 2025 Q1
  Conclude potential normative work
Overall plan
FS_NG_RTC_SEC_Ph2 overall plan

## Slide 3
General
  TR 33.790 v0.3.0 contains the scope, assumptions clauses, 3 key issues:
    Key Issue #1: Third party specific identities with Rel-18 key issue formulation, Editor’s Note for SA2 progress
    Key Issue #2: Security of IMS based Avatar Communication
    Key Issue #3: Security and privacy aspects of IMS DC capability exposure
  All key issues depend on the progress of the corresponding SA2 study
  The TR includes 9 solutions, 4 for KI#1, 4 for KI#2 and 1 for KI#3, most of which have Editor’s Notes stating the dependency of the SA3 study on the SA2 study.
Dependencies:
  SA2 study documented in TR 23.700-77 and SA3 concluded solutions depend heavily on concluded SA2 solutions
  SA2 and SA3 meetings are overlapping.
Contentious Issue:
  None
Risks:
  Normative work takes more time due to dependencies and overlapping SA2 and SA3 meetings.
FS_NG_RTC_SEC_Ph2 status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020038 | Study on the security support for the Next Generation Real Time Communication services phase 2 | FS_NG_RTC_SEC_Ph2 | Rel-19 | S3 | Dec-2024 | 17% | 40% | TR 33.790

## Slide 4
Pending issues
  SA2 study dependency
Dependencies:
  All SA3 concluded solutions depend on the SA2 concluded solutions
TUs consumed
  SA3#115: 0.5 TUs
  SA3#115Adhoc-e: 0.5 TUs
  SA3#116: 0.5 TUs
TUs remaining
  SA3#117-SA3#120 (2025): 4.5 TUs for this study item and the potential work item corresponding to the study
Plan for completion
  See earlier slide 2
FS_NG_RTC_SEC_Ph2 pending work and plan for completion