## Slide 1: SA WG3 Status report for MCXSec4
Tim Woodward
Motorola Solutions, Inc

## Slide 2
TUs planned
  0.3
In SA3#119 meeting -
  Finalize security architecture for MC Logging
  Finalize security architecture for MC Gateway UE
Overall plan
MCXSec4 overall plan

## Slide 3
General
  Feature is progressing according to plan
Dependencies:
  SA6 MC Logging Architecture
  SA6 MC Gateway Architecture
Contentious Issue:
  None
Risks:
  None identified
MCXSec4 status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020035 | Mission Critical security enhancements phase 4 | MCXSec4 | Rel-19 | S3 | Jun -2025 | 10 | 10 | TS 33.180

## Slide 4
Pending issues
  NONE
TUs consumed
  SA3#116 – 0.00
TUs remaining
  SA3#116 - 0.27
Plan for completion
  TSG#106
MCXSec4 pending work and plan for completion