## Slide 1: SA WG3 Status report for FS_ZTS
Sheeba Backia Mary B.
Lenovo

## Slide 2
August meeting (SA3#108-e):
  Agree on the main key issue(s) for the SID.
  Main Key Issue includes: ‘Need for continuous trust evaluation’ and ‘Scenarios which can benefit from trust evaluation outcome’.
October Meeting (SA3#108Adhoc-e):
  Discuss and agree on Solution(s) for the agreed main Key Issue(s).
  Also, discuss and agree on additional secondary Key Issues (if any relevant) for the SID.
November Meeting (SA3#109):
  Discuss and agree on solution refinements/evaluations for the main key issue(s) and new solutions for additional key issues (if any exist).
  Reach conclusions for the Main Key Issue(s).
January/February Meeting (SA3#109Adhoc/SA3#110):
  Initiate Normative work.
  Reach Conclusions for the Secondary Key Issue(s) if any.
April Meeting (SA3#110Adhoc):
  Progress Normative work.
May Meeting (SA3#111):
  Complete Normative work.
Over-all plan
FS_ZTS Status

## Slide 3
Key Issues | Solutions | Solution status
Yet to be agreed! None | None | 
TR 33.894 Summary
FS_ZTS Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Agreed Skeleton and Scope.
SA3#108
Aug 22-26, 2022
Deadline to introduce new main Key Issues
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce solutions and new additional secondary Key Issues.
SA3#109
Nov 14-18, 2022
Conclusions & Normative work

## Slide 4
General
  TR 33.894 v0.1.0 contains scope. The main key issue is yet to be agreed.
    Main Key Issue includes: ‘Need for continuous trust evaluation’ and ‘Scenarios which can benefit from trust evaluation outcome’.
Dependencies:
  None (the SID has no RAN impacts)
FS_ZTS status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960038 | Study on Zero Trust Security principles in mobile networks | FS_ZTS | Rel-18 | S3 | Mar-2023 | 0% | 5% | TR 33.894

## Slide 5: FS_ZTS status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  None for RAN and none determined yet for SA2.
Contentious Issue:
  None.
Focus for the Next Meeting :
  The description of the main key issue, ‘Need for continuous trust evaluation’ has be aligned across different companies in SA3.
Overall Plan:
  See dedicated slide (No. 2).
Risks:
  If alignment can’t be reached for the main Key Issue description, ‘Need for continuous trust evaluation’, it will impact the SID progress, and completion.