## Slide 1: SA WG3 Status report for FS_5WWC_Ph2_Sec
Saurabh Khare
Nokia

## Slide 2
History:
  SA2 reference: SA2 5WWC_Ph2 work has progressed well with 25 solution in the SA2 TR 23700-17. In Aug meeting, conclusion will start
  In June SA3 meeting, 6 KIs were presented but only 3 KIs were agreed for the TR 33.887.
August meeting:
  Last meeting to add key issues
  Add solutions for current key issues KIs
October meeting:
  Last meeting to add solutions
  Solution evaluations
November meeting:
  Solution evaluations
  Conclusions for key issues
  Agree on WID
January/February meeting:
  Start normative work
April meeting:
  Normative work
May meeting:
  Finalize normative work
Overall plan
FS_5WWC_Ph2_Sec Status

## Slide 3
Key Issues | Solutions | Solution status
#1: Authentication of AUN3 device behind RG and supporting EAP | Not presented New proposed KI in 107Adhoc | 
#2: Security aspect of slice information exposure of N3IWF/TNGF to UE | Not presented New proposed KI in 107Adhoc | 
#3: Security aspect of slice information exposure of N3IWF/TNGF | Not presented New proposed KI in 107Adhoc | 
TR Summary
FS_5WWC_Ph2_Sec Status
SA3#107 Adhoc-e Jun27-July1st 2022
TR scope & skeleton and Key Issues proposals
SA3#108
Aug 22-26, 2022
Deadline to introduce new Key Issues
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new solution proposals
SA3#109
Nov 14-18, 2022
Solution completion
Conclusions

## Slide 4: FS_5WWC_Ph2_Sec status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960030 | Study on Security aspects for 5WWC Phase 2 | FS_5WWC_Ph2_Sec | Rel-18 | S3 | Mar-2023 | 0% | 10% | 3 new KIs added in TR 33.887
General
  TR 33.887 v0.1.0 contains 3 issues
  Study addresses the security aspects of new devices introduced in SA2 5WWC and the security aspects of slice information exposure of N3IWF/TNGF
Dependencies:
  SA3 solution procedure must be aligned with SA2; there are currently no evaluations or conclusions in the SA2 TR.

## Slide 5: FS_5WWC_Ph2_Sec status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  SA3 solution procedure must be aligned with SA2; there are currently no evaluations or conclusions in the SA2 TR.
Contentious Issue:
  None
Focus for the Next Meeting :
  Add solutions (KI 1-3)
  Last meeting to add key issues
Overall Plan:
  See dedicated slide
Risks:
  SA2 starts conclusion on August meeting. SA3 may delay to study KI with 5GS requirements and corresponding solutions at the October meeting.