## Slide 1: SA WG3 Status report for ‘FS_ACM_SBA’
Rapporteur
Nokia

## Slide 2
In May meeting (first meeting after SID Approval): concentrate on key issues. New 9 key issues were approved.
In June meeting new 7 solutions have been approved addressing Key issues #1, #2, #4, #5, #6.
New WID to prepare normative work: Next meeting SA3#108 –bis-e (10.10 – 14.10)
Deadline to introduce new solutions: Next meeting SA3#108-bis-e (10.10 – 14.10) – no more solutions will be accepted for technical report.
Complete the evaluation and normative of all solutions in Q1 2023 (first meeting).
Overall plan
‘FS_ACM_SBA’ Status

## Slide 3
Key Issues | Solutions | Solution status
KI#1: Single certificate management protocol and procedures | New solution for key issue 1 | ENs, Work in progres
 | A new solution of using CMP for certificate enrolment and renewal | ENs, Work in progress
KI#2: Security protection of NF certificate enrolment | Solution for secure initial enrolment of NF certificates | ENs, Work in progress
KI#3: NF Certificate Update |  | 
KI#4: Trust Chain of Certificate Authority Hierarchy | New solution on Cross-Certification Based Trust Chain in the SBA Architecture | ENs, Work in progress
 | New solution on Interconnection CA Based Trust Chain in the SBA Architecture | ENs, Work in progress
KI#5: Certificates revocation procedures | New solution for key issue 3 and 4 based on OCSP | ENs, Work in progress
KI#6: Relation between certificate management lifecycle and NF management lifecycle | A solution for certificate and NF lifecycle management relation | ENs, Work in progress
KI#7: Multiple certificates to be associated with a Network Function |  | 
KI#8: Trusted Network Function instances identifiers |  | 
KI#9: Automated Certificate Management for Network Slicing |  | 
TR Summary
‘FS_ACM_SBA’ Status

## Slide 4
General
  Farly good progres, although numerous editorial notes in proposed solutions to be fixed.
  Still four Key issues have not been addressed so far with solutions
  Only four companies have contributed with solutions in this meeting
Dependencies:
  None
‘Feature Acronym’ status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
920022 | Study on Standardising Automated Certificate Management in SBA | FS_ACM_SBA | Rel-18 | S3 | Mar-2023 | 35% | 60% | TR 33.876

## Slide 5: ‘Feature Acronym’ status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  None for RAN and none determined yet for SA2
Contentious Issue:
  One of the noted proposals used Remote Attestation (RA) for establishing initial trust. RA is being studied in FS_SIV, and the solution was objected with the argument that RA should not be studied in two different SIDs.
Focus for the Next Meeting :
  Complete all solutions in October
  Normative work for Q1 2023
Overall Plan:
  See dedicated slide
Risks:
  KI completion in Q1 2023 (due to lack of meetings to make progres and get agreements). Note that Automatic Certificate Management in SBA has not been addressed so far in previous releases, although it is an obvious features to enable others like TLS in SBA, so we should not extend the study.