## Slide 1: SA WG3 Work Plan for FS_AIML
Marcus Wong
OPPO

## Slide 2
August meeting
  Potential CC before meeting to discuss way forward
  Continue key issue discussion, make progress to have initial KI agreements
October meeting
  Continue key issue
  Entertain potential solution(s) and possible potential evaluation(s)
November meeting
  Last meeting to add new solutions
  Solution evaluations
  First conclusions
  Discussion on potential WID objectives. Preliminary agreements on objectives.
January meeting/February
  Conclusions for all key issues
  Potential WID agreement
  Potential normative work
April meeting
  Potential normative work
May meeting
  Finalize potential normative work
Overall plan
FS_AIMLStatus

## Slide 3
Key Issues | Solutions | Solution status
None so far. | None so far. | N/A
TR 33.898 Summary
FS_AIML Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Skeleton and Scope
Key Issues and Solution proposals
SA3#108
Aug 22-26, 2022
First potential new Key Issue(s)
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
Potential Solution
SA3#109
Nov 14-18, 2022
Solutions
Conclusions & Normative work

## Slide 4
General
  TR 33.898 v0.1.0 contains the scope and background clauses.
Dependencies:
  SA2 has 7 stable KI identified and 47 solutions captured in TR 23.700-80, including several with security dependencies identified.
  User consent and privacy aspect of the FS_AIML are to be coordinated with both FS_UC3S_Ph2 and FS_Id_Prvc studies
  Reply LS on Network Information Exposure UE is awaiting SA1 clarification.
  SA1 and SA3 has partial meeting overlap in August and full overlap in November while SA2 and SA3 has partial meeting overlap in August and full overlap October and November. Meeting overlap may delay any potential LS or LS reply to/from involved WGs .
  It might be necessary for offline SA3 teleconferences in between regular meetings.
FS_AIML status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960037 | Study on the security and privacy of AI/ML-based services and applications in 5G | FS_AIML | Rel-18 | S3 | Mar-2023 | 0 | 5% | TR 33.898

## Slide 5: FS_AIML status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  None for RAN
  SA2 s since only the scope and background clauses were added in the TR.
Contentious Issue:
  All KIs proposed in SA3#107Adhoc-e .
Focus for the Next Meeting :
  First key issue agreements
Overall Plan:
  See dedicated slide
Risks:
  One or more company/companies continue blocking progress of KI discussion and conclusion.
  If no KI can be agreed during SA3#108-e, FS_AIML schedule may be severely jeopardized.