## Slide 1: SA WG3 Status report for ‘FS_AKMA_Ph2’
Xiaoting Huang
China Mobile

## Slide 2
Only two main key issues are scoped for now:
Key issue 1: AKMA roaming
Key issue 2: Intoducing Authentication Proxy (AP)
August meeting (prefer to be added in the agenda or added into the November meeting):
  Finalize the key issues!
  A SA3/SA3-LI joint-call will be arranged to focus on the roaming key issue and related solutions( if possible)
  Add solutions and evaluations
  Add conclusions if any
  Last meeting for extending SID objectives!
October meeting
  Last meeting to add/update solutions!
  Add conlcusions
  Send the TR for information/approval
  Agree on the WID based on the conclusions
January/February meeting:
  Start normative work.
  Finalize the TR
April meeting:
  Normative work
May meeting:
  Finalize normative work
Overall plan
‘FS_AKMA_Ph2’ Status

## Slide 3
Key Issues | Solutions | Solution status
Key Issue #1: Support for AKMA roaming scenario | 6 solutions | All lack of details of LI consideration
Key Issue #2: Introducing the Authentication proxy into AKMA | 1 solution | EN of FQDN configuration
TR Summary
‘FS_AKMA_Ph2’ Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues and Solution proposals
SA3#108
Aug 22-26, 2022
Deadline to introduce new Key Issues
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce/update solutions
Conclusions & TR sent for indormation/approval
SA3#109
Nov 14-18, 2022
Or not removing from the November meeting if the study cannot be included in the August meeting

## Slide 4
General
  TR 33.737 v0.2.0 contains 2 key issues and 7 solutions
Dependencies:
  None
‘FS_AKMA_Ph2’ status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
950018 | Study on AKMA Phase 2 | FS_AKMA_Ph2 | Rel-18 | S3 | Dec-2022 | 15% | 35% | 1 updated key issue and 7 new solutiosn are added to TR 33.737

## Slide 5: ‘FS_AKMA_Ph2’ status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  None
Contentious Issue:
  There are different understandings/interpretation of LI requirements.
Focus for the Next Meeting :
  Finalize the key issues, especially KI#1 with LI requirements agreed
  Solutions for both key issues
Overall Plan:
  See dedicated slide, slide #2.
Risks:
  Only 1 meeting left to complete the SID if not included in both August& November meeting, as the SID was targeted at Dec, 2022.
  Request to be included in the agenda of either August or November meeting.