## Slide 1: SA WG3 Status report for FS_HN_Auth
He Li
Huawei

## Slide 2
August meeting:
  not included in draft agenda, if included, then addressing ENs, discuss evaluations, and draw potential solutions. Open for new solutions, but not recommended.
Prior to the October meeting (in case it is not included in August meeting)
  1st offline CC to address ENs, evaluations, accept new solutions. (before August meeting).
  2nd offline CC, alternatively, by email to collect way forward suggestion. (before October meeting)
October meeting, accept contributions are:
  addressing Editor’s Note,
  The new solutions
    that was discussed in the 1st offline CC.
    No strong obstacle based on the 1st offline CC.
  Evaluations, conclusions.
  Cleanups
  New KI is not recommended.
November meeting
  TR: Not included in the draft agenda, if in, then finalized the conclusions, and sent for approval.
  submit the WID proposal.
January/February meeting:
  conclusions and sent for approval (if is not included in November meeting).
  Normative work ( if WID is agreed in November meeting, otherwise, it should be WID proposal)
April meeting:
  Normative work
May meeting: Finalize normative work
Overall plan
‘FS_HN_Auth’ Status

## Slide 3
TR Summary
‘FS_HN_Auth’ Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues and Solution proposals
SA3#108
Aug 22-26, 2022
Deadline to introduce new Key Issues
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
SA3#109
Nov 14-18, 2022
Conclusions & Normative work
2 Key issues:
  Key Issue #1: Ability of the home network to trigger primary authentication
  Key Issue #2: Signalling overload due to running the primary authentication for Kaf refresh
9 solutions:
  Solution #1: HN triggering primary authentication for various scenarios
  Solution #2: UDM triggered primary authentication
  Solution #3: Home network triggered authentication solution for 4G to 5G interworking
  Solution #4: UDM initiated primary authentication based on a NF request
  Solution #5: Using the UDM to start home triggered authentications
  Solution #6: UDM initiated primary authentication based on AUSF request
  Solution #7: UDM initiated Primary Authentication
  Solution #8: Solution to enable UDM in the HN to trigger Primary Authentication
  Solution #9: AMF initiated primary authentication based on AUSF request
No evaluations
No conclusions

## Slide 4
General
  9 new solutiosn are approved in the second meeting
  21 Editor's Note
  No evaluations to all solutions.
  No conclusions.
Dependencies:
  None (the SID has no RAN impacts)
‘FS_HN_Auth m’ status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
950020 | Study of Security aspect of home network triggered primary authentication | FS_HN_Auth | Rel-18 | S3 | DEC-2022 | 30% | 60% | TR 33.741

## Slide 5: ‘FS_HN_Auth’ status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  None for RAN and none determined yet for SA2
Contentious Issue:
  UDM basis vs. AUSF basis
  Whether SoR/UPU counter wrap around, and interworking from 4G to 5G is included.
  Whether to use new SBI or reuse old SBI.
Focus for the Next Meeting :
  Complete all solutions in October
  Draw conclusions
Overall Plan:
  See dedicated slide
Risks:
  Only one meeting is left ( 3 meetings totally), conclusions may not be well defined for normative work.