## Slide 1: SA WG3 Status report for FS_NR_AIML_NGRAN_SEC
Vlasios Tsiatsis
Ericsson

## Slide 2
August meeting
  First key issue agreements
October meeting
  Add further key issues depending on the progress of RAN3
  First potential solutions and potential evaluations
November meeting
  Last meeting to add new solutions
  Solution evaluations
  First conclusions
  Discussion on potential WID objectives. Preliminary agreements on objectives.
January meeting/February
  Conclusions for all key issues
  Potential WID agreement
  Potential normative work
April meeting
  Potential normative work
May meeting
  Finalize potential normative work
Overall plan
FS_NR_AIML_NGRAN_SEC Status

## Slide 3
Key Issues | Solutions | Solution status
None so far. | None so far. | N/A
TR 33.877 Summary
FS_NR_AIML_NGRAN_SEC Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues and Solution proposals
SA3#108
Aug 22-26, 2022
Deadline to introduce new Key Issues
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
SA3#109
Nov 14-18, 2022
Conclusions & Normative work

## Slide 4
General
  TR 33.877 v0.1.0 contains the scope and background clauses.
Dependencies:
  RAN3 has agreed on a WID for the RAN AI/ML framework in April but has not started working on the normative work yet. It is expected that RAN3 starts working on normative work in August (RAN3#117-e, Aug 15-24). SA3’s meeting will have some results of the RAN3 discussion during the SA3 meeting but not before submission.
  October and November meetings for SA3 and RAN3 are overlapping.
  It is recommended that SA3 company delegates coordinate with their RAN3 colleagues to progress the SA3 work in parallel.
  It might be necessary for offline SA3 teleconferences in between regular meetings.
FS_NR_AIML_NGRAN_SEC status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960031 | Study on the security aspects of Artificial Intelligence (AI)/Machine Learning (ML) for the NG-RAN | FS_NR_AIML_NGRAN_SEC | Rel-18 | S3 | Mar-2023 | 0 | 2% | TR 33.877

## Slide 5: FS_NR_AIML_NGRAN_SEC status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  None for RAN3 since only the scope and background clauses were added in the TR.
Contentious Issue:
  None for the moment.
Focus for the Next Meeting :
  First key issue agreements
Overall Plan:
  See dedicated slide
Risks:
  SA3 and RAN3 meetings are mostly overlapping in 2022.