## Slide 1: SA WG3 Status report for FS_Ranging_SL_Sec
Wei Lu
Xiaomi

## Slide 2
August meeting:
  Update the existing key issue as needed
  Agree on key issue for Direct Communication security
  Add new key issues based on the status of SA2 work
  Start to add solutions for key issues
October meeting:
  Last meeting to add/update key issues, based on progress at SA2’s August meeting
  Add solutions for key issues and update existing solutions as needed
  Start to add solution evaluations
November meeting:
  Last meeting to add new solutions and update existing solutions as needed
  Add solution evaluations
  Start to add conclusions for key issues
  Agree on WID with first set of objectives
January/February meeting:
  Start normative work
  Complete the conclusions for key issues
  Last meeting for extending WID objectives
April meeting:
  Normative work
May meeting:
  Finalize normative work
Overall plan
FS_Ranging_SL_Sec Status
Notes: Key issues added during June and August meetings should be concluded in November.
(e.g. Resolve the ENs in the agreed key issues)

## Slide 3
Key Issues | Solutions | Solution status
Privacy protection for Ranging/SL Positioning services | None | 
Authorization for Ranging/Sidelink Positioning Service | None | 
Protection of discovery procedure | None | 
TR 33.893 Summary
FS_Ranging_SL_Sec Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues
SA3#108
Aug 22-26, 2022
Key Issues and Solution proposals
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
SA3#109
Nov 14-18, 2022
Conclusions

## Slide 4
General
  TR 33.893 v0.1.0 contains the scope and three key issues
Dependencies:
  SA2’s work on FS_Ranging_SL, TR 23.700-86 v0.3.0, completion rate 60%, end date Dec-2021.
  Next SA2 meeting 17-26 August 2022, i.e. SA2 will not have progressed at SA3’s August meeting
FS_Ranging_SL_Sec status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960036 | Study on Security Aspects of Ranging Based Services and Sidelink Positioning | FS_Ranging_SL_Sec | Rel-18 | S3 | Mar-2023 | 0% | 10% | TR 33.893

## Slide 5: FS_Ranging_SL_SEC status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  None for RAN and none determined yet for SA2
Contentious Issue:
  Key issue on Direct Communication Security was not agreed at SA3#107adhoc-e
Focus for the Next Meeting (August):
  Agree on key issue for Direct Communication Security
  Add further key issues based on current status of SA2 work
  Add solutions for the agreed key issues
Overall Plan:
  See dedicated slide
Risks:
  None identified