## Slide 1: SA WG3 Status report for FS_eNPN_Ph2_SEC
Christine Jost
Ericsson

## Slide 2
August meeting:
  Agree on key issue for authentication of UE access to hosting network.
  Add further key issues based on current status of SA2 work
  Add solutions for key issue on security of non-3GPP access
October meeting:
  Last meeting to add new key issues, based on progress at SA2’s August meeting
    Security issues of concluded solutions and ongoing normative work need to be pointed out at any stage of the work and will be addressed accordingly (directly in normative work if necessary), but new security use cases should not be proposed beyond the October meeting.
  Add solutions and solution evaluations
November meeting:
  Last meeting to add new solutions
  Solution evaluations
  Conclusions. Key issues added during June and August meetings should be concluded in November.
  Agree on WID with first set of objectives
January/February meeting:
  Start normative work.
  Conclusions for key issues added in October.
  Last meeting for extending WID objectives
April meeting:
  Normative work
May meeting:
  Finalize normative work
Overall plan
FS_eNPN_Ph2_SEC Status

## Slide 3
Key Issues | Solutions | Solution status
Security of non-3GPP access for SNPN | None | 
TR 33.858 Summary
FS_eNPN_Ph2_SEC Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues
SA3#108
Aug 22-26, 2022
Key Issues and Solution proposals
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
SA3#109
Nov 14-18, 2022
Conclusions

## Slide 4
General
  TR 33.858 v0.1.0 contains scope and one key issue (Security of non-3GPP access for SNPN)
Dependencies:
  SA2’s work on FS_eNPN_Ph2, TR 23.700-08 v1.0.0, completion rate 50%, end date Dec-2020.
    Key issues on mobility between SNPNs, non-3GPP access for SNPNs, and access to localized services
    Solutions available to all key issues
    No evaluations or conclusions so far
  Next SA2 meeting 17-26 August 2022, i.e. SA2 will not have progressed at SA3’s August meeting
FS_eNPN_Ph2_SEC status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960033 | Study on security aspects of enhanced support of Non-Public Networks phase 2 | FS_eNPN_Ph2_SEC | Rel-18 | S3 | Mar-2023 | 0% | 10% | TR 33.858

## Slide 5: FS_eNPN_Ph2_SEC status after SA3#107Adhoc-e
Contentious Issue:
  Key issue on authentication of UE access to hosting network was not agreed at SA3#107adhoc-e
Focus for the Next Meeting (August):
  Agree on key issue for authentication of UE access to hosting network.
  Add further key issues based on current status of SA2 work
  Add solutions for key issue on security of non-3GPP access
Overall Plan:
  See dedicated slide
Risks:
  Tight schedule, especially if new key issues need to be added at October meeting based on further progress in SA2