## Slide 1: SA WG3 Status report for ‘FS_SNAAPPY’
Alf Zugenmaier
NTT DOCOMO

## Slide 2
In July: achieve common understanding of use cases.
In August meeting: agree key issues
Before October meeting: conf calls to work on solutions
October meeting: agree solutions, work on conclusions
November meeting: finalize conclusions
Overall plan
‘FS_SNAAPPY’ Status

## Slide 3
Key Issues | Solutions | Solution status
authentication and authorization of UE in UE originated API invocation | none | -
TR Summary
‘FS_SNAAPPY’ Status
SA3#108
Aug 22-26, 2022
Stable set of Key Issues
SA3#108 Adhoc-e Oct 10-14, 2022
Agree solutions
SA3#109
Nov 14-18, 2022
Conclusions

## Slide 4
General
Dependencies:
‘FS_SNAAPPY’ status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
9200?? | Study on SNAAPP securitY | FS_SNAAPPY | Rel-18 | S3 | Dec 22 | 0% | 10% | TR 33.884

## Slide 5: ‘FS_SNAAPPY’ status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  SA6 waiting for progress in SA3
Contentious Issue:
  None
Focus for the Next Meeting :
  Complete key issues in August
Overall Plan:
  See dedicated slide
Risks:
  KI overload (due to diverging use case understanding)