## Slide 1: SA WG3 Status report for FS_EDGE_Ph2
Bo Zhang
Huawei

## Slide 2
In August meeting:
  Concentrate on key issues (new and updated).
  Evaluation on solutions for KI 2.2 “Authentication mechanism selection between EEC and ECS/EES” are welcomed.
In October meeting:
  Concentrate on solutions and evaluation for KI 2.2 (new and updated).
  New key issues are not expected after October meeting . (However, considering the timeline of SA2 and SA6 group, SA2/SA6-related new key issue is also welcome if any.)
In November meeting:
  Concentrate on solution update and conclusion.
  The TR is expected to sent for information.
  WID proposal may be submitted for discussion and endorsement.
In January/February meeting:
  Start normative work.
  Additional conclusion in TR may also be added. The TR is expected to be sent for approval
In April meeting:
  Continue the normative work
In May meeting:
  Finalize normative work
Overall plan
FS_EDGE_Ph2 Status

## Slide 3
Key Issues | Solutions | Solution status
Key issue #1.1: How to authorize PDU session to support local traffic routing to access an EHE in the VPLMN | None | None
Key Issue #2.1: Authentication and authorization of the EEC/UE by the ECS/EES | 2 | Added in SA3 #107adhoc
Key issue #2.2: Authentication mechanism selection between EEC and ECS/EES | 9 | Added in SA3 #107adhoc Controversial issues: How to select the authentication mechanism Whether authentication failure should be avoided.
Key issue #2.3: Authentication and Authorization between V-ECS and H-ECS | None | None
Key issue #2.4: Transport security for the EDGE10 interface | None | None
TR Summary
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues proposals
SA3#108
Aug 22-26, 2022
Key Issues proposals
New solutions
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
New solutions
SA3#109
Nov 14-18, 2022
Conclusions
WID proposal
FS_EDGE_Ph2 Status

## Slide 4
General
  TR 33.739 v0.2.0 contains scope, 5 key issues, and 11 solutions.
Dependencies:
  SA2 SID (TR 23.700-48: "5G System Enhancements for Edge Computing; Phase 2")
    Solutions available to all key issues
    No conclusions so far
  SA6 SID (TR 23.700-98: "Study on Enhanced architecture for enabling Edge Applications ")
    Solutions available to all key issues
    No conclusions so far
FS_EDGE_Ph2 status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
950023 | Study on Security Enhancement of support for Edge Computing — phase 2 | FS_EDGE_Ph2 | Rel-18 | S3 | Dec-2022 | 30% | 40% | TR 33.739

## Slide 5
Contentious Issue:
  Key issue #2.2: Authentication mechanism selection between EEC and ECS/EES
Focus for the Next Meeting :
  concentrate on key issues (new and updated), and the security baseline for the KI #2.2
  Solutions are also welcome.
Overall Plan:
  See dedicated slide
Risks:
  Conclusion on Key Issue #2.2 is not achieved in Rel17. No consensus can be seen from the last meeting. Companies are suggested to consider how to securely establish the authentication between EEC and EES/ECS correctly. If the authentication failure can not be avoided, the whole procedure may not be workable in reality.
FS_EDGE_Ph2 status after SA3#107Adhoc-e