## Slide 1: SA WG3 Status report for FS_NG_RTC_SEC
Fei Li
Huawei

## Slide 2
In August meeting:
  Concentrate on key issues (new and updated).
  New solutions for all key issues.
In October meeting:
  Concentrate on solutions and evaluation for KI#1.
  New solutions for other KIs if necessary.
  New key issues are not expected after October meeting .
In November meeting:
  Concentrate on solution update and conclusion.
  The TR is expected to sent for information.
  WID proposal may be submitted for discussion and endorsement.
In January/February meeting:
  Start normative work.
  Additional conclusion in TR may also be added. The TR is expected to be sent for approval
In April meeting:
  Continue the normative work
In May meeting:
  Finalize normative work
Overall plan
FS_NG_RTC_SEC Status

## Slide 3
Key Issues | Solutions | Solution status
Key issue #1: Third party specific user identities | None | None
TR Summary
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues proposals
SA3#108
Aug 22-26, 2022
Key Issues proposals
New solutions
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
New solutions
SA3#109
Nov 14-18, 2022
Conclusions
WID proposal
FS_NG_RTC_SEC Status

## Slide 4
General
  TR 33.890 v0.1.0 contains scope, 1 key issue.
Dependencies:
  SA2 SID (TR 23.700-87: "Study on system architecture enhancement for next generation real time communication")
    Solutions available to all key issues
    No conclusions so far
FS_NG_RTC_SEC status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960032 | Study on security support for Next Generation Real Time Communication services | FS_NG_RTC_SEC | Rel-18 | S3 | Dec-2022 | NA | 10% | TR 33.890

## Slide 5
Contentious Issue:
  Key issue #1:Third party specific user identities
Focus for the Next Meeting :
  concentrate on key issues (new and updated)
  Solutions are also welcome.
Overall Plan:
  See dedicated slide
Risks:
  May delay due to no clear SA2 conclusion on architectural assumption for 3rd ID aspects.
FS_NG_RTC_SEC status after SA3#107Adhoc-e