## Slide 1: SA WG3 Status report for FS_ZTS
Sheeba Backia Mary B.
Lenovo

## Slide 2
August meeting (SA3#108-e):
  Agree on the main key issue(s) for the SID (KIs were not agreed. But agreed a tenet evaluation template).
  Main Key Issue includes: ‘Need for continuous trust evaluation’ and ‘Scenarios which can benefit from trust evaluation outcome’.
October Meeting (SA3#108Adhoc-e):
  Agree on the key issue(s) for the SID. (Agreed partial KI details. KIs threat and security requirement was not agreed. But agreed some tenet evaluation information (e.g., T1, T2, T3, T5, T6, T7)
  Discuss and agree on evaluation information for the Tenets.
November Meeting (SA3#109):
  A Key Issue was agreed. (Agreed partial KI threat and security requirement was agreed. T7 evaluation was completed.
  A tenet evaluation was refined (e.g., T7).
January Meeting (SA3#109-bis):
  Discuss and agree on solutions for KI#1.
  Discuss and agree on additional KIs (if any).
  Resolve EN in Key Issue#1.
February Meeting (SA3#110):
  The ENs in KI#1 Security Requirement was cleaned up.
  Discussed solutions to KI#1, but there was no approval/consensus reached on the solutions.
April Meeting (SA3#110-bis-e):
  Discuss and agree on solutions for KI#1.
  Discuss and agree on additional KIs (if any). Completion of Tenet 5 and 6 evaluations.
  Draw initial conclusions for the Key Issue #1.
May Meeting (SA3#111):
  Complete the evaluations (if any left out) and complete the conclusions.
  WID proposal is planned to be submitted for discussion and approval.
  Send the TR 33.894 for approval
  Initiate the Normative work.
Aug Meeting (SA3#112):
  Normative work completion
Over-all plan
FS_ZTS Status
The SID AI was not on agenda

## Slide 3
Key Issues | Solutions | Solution status
KI#1 Agreed (Key Issue #1: Need for continuous security monitoring) | None | 
TR 33.894 Summary
FS_ZTS Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Agreed Skeleton and Scope.
KI not agreed.
SA3#108
Aug 22-26, 2022
Agreed Tenet evaluation template.
KI not agreed.
SA3#108 Adhoc-e Oct 10-14, 2022
Partial Key Issue Agreed.
SA3#109
Nov 14-18, 2022
Key Issue Security requirement agreed.
SA3#110-e
Nov 14-18, 2022
Agree solution to KI#1
SA3#110
Nov 14-18, 2022
Key Issue Sec. req. section cleaned-up.

## Slide 4
General
  TR 33.894 v0.5.0 contains scope, tenet evlauation details (complete for Tenet 1,2,3,7 and partial/incomplete for other Tenets) and 1 main key issue.
    Main Key Issue#1 includes: ‘Need for continuous security monitoring’.
Dependencies:
  None (this SID has no RAN impacts)
FS_ZTS status after SA3#110
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960038 | Study on Zero Trust Security principles in mobile networks | FS_ZTS | Rel-18 | S3 | Sept-2023 | 20% | 30% | TR 33.894

## Slide 5: FS_ZTS status after SA3#110
  SA2/RAN impacts and dependencies:
  None for RAN and none determined yet for SA2.
Contentious Issue:
  Consensus could not be reached on tenet evaluation for Tenet 5 and 6.
    T5: Monitoring and measurement related to integrity and security posture of NFs.
    T6: Access control related to assessing threats, adapting, and continually reevaluating trust of NFs.
  In SA3#110 meeting solutions to KI#1 were objected by 2 companies to be recorded in the TR as part for the study even when the solution revisions had the evaluation sections open.
Focus for the Next Meeting :
  Solution discussion for KI#1.
    Solutions proposal and tenet evaluation completion proposal are most welcome from all ZTS colleagues and related companies.
  Additional Key Issue proposal (if any).
Overall Plan:
  See dedicated slide (No. 2).
Risks:
  Already solution discussion phase got delayed due to late alignment on KI#1. Similar traces were observed in the solution discussions in SA3#110 meeting. Looking foward to handle the solution phase more constructively with all involved ZTS colleagues to keep-up the work-progress and meet the Schedule in slide 2.