## Slide 1: SA WG3 Status report for FS_5GSAT_Sec
Wei Lu
Xiaomi

## Slide 2
October meeting:
  Scope approved
  One key issue added with no security threats and requirements
November meeting:
  KI#1 updated with threat analysis
  Another proposed new KI is pending on the reply from CT1 to SA2’s LS
January meeting:
  Updated KI#1 with potential requirements
February meeting:
  No progress
April meeting:
  Add new solutions for KI#1
  Propose identified new KI(s)
May meeting:
  Add conclusions to the KIs
  Propose WID if needed
August meeting:
  Start normative work
Overall plan
FS_5GSAT_Sec Status
Notes: Key issues added during June and August meetings should be concluded in November.
(e.g. Resolve the ENs in the agreed key issues)

## Slide 3
General
  TR 33.700-28 v0.2.0 contains one key issue (with EN)
Dependencies:
  SA2 SID: TR 23.700-28 v1.1.0 100% completed
  SA2 WID: living documents (to TS 23.501, TS 23.502, etc.) in progress
FS_5GSAT_Sec status after SA3#110
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
970028 | Study on Security Aspects of Satellite Access | FS_5GSAT_Sec | Rel-18 | S3 | Q3-2023 | 15% | 25% | TR 33.700-28

## Slide 4: FS_Ranging_SL_SEC status after SA3#110
  SA2/RAN impacts and dependencies:
  None for RAN
  SA2 conclusions already completed but too general without confirmative procedures, and even involved functionalities are still in discussion
Contentious Issue:
  Progress on KI#1 pending on open discussion in SA2 normative work
Focus for the Next Meeting (Apr.):
  Add solutions for KI#1
  Discuss on identified new KI(s)
Overall Plan:
  See slide #2
Risks:
  There are still open issues in SA2 normative work, which SA3 study progress depends on
  Exception may be requested according to the current progress