## Slide 1: SA WG3 Status report for FS_USIA
Andreas Kunz
Lenovo

## Slide 2
November meeting:
  Last meeting to add new solutions 
  Solution evaluations 
  Conclusions. Key issues added during June and August meetings should be concluded in November. 
  Agree on WID with first set of objectives 
  Send TR 33.892 for information 
January meeting:
  Solution evaluations 
  Conclusions 
  Agree on WID with first set of objectives 
  Send TR 33.892 for information 
February meeting
  Start normative work. 
  Last meeting for extending WID objectives 
  Solution evaluations 
  Send TR 33.892 for information 
  Send TR 33.892 for approval 
April meeting:
  Conclusions
  Agree on WID with first set of objectives
  Send TR 33.892 for approval
  Start Normative work
May meeting:
  Finalize normative work
Overall plan
FS_USIA Status

## Slide 3
Key Issues | Solutions | Solution status
Determination of application identification | Provide additional authentication information to enhance URSP policy enforcement. | Evaluation agreed
Determination of application identification | Solution on enhancing the URSP rule with certificate fingerprint | Evaluation agreed
Determination of application identification | Solution on prevention of URSP rule misuse by a non-genuine application using home network anchor | Evaluation TBD
TR 33.892 Summary
FS_USIA Status
SA3#109 AdHoc
Jan 16-20, 2023
Conclusions
SA3#110
Feb 20-24, 2023
Solution Evaluations
TR for Information
SA3#110 Adhoc-e Apr 17-21, 2023
Conclusions
TR for approval
WID
SA3#111
Mar 22-26, 2023
Normative work

## Slide 4
General
  TR 33.892 v0.4.0 contains one key issue and 3 solutions (Determination of application identification)
  Evaluations of two solutions were agreed
  TR sent for Information
Dependencies:
  None
FS_USIA status after SA3#110
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960035 | Study on URSP rules to securely identify applications | FS_USIA | Rel-18 | S3 | Mar-2023 | 50% | 80% | TR 33.892

## Slide 5: FS_USIA status after SA3#110
Contentious Issue:
  None
Focus for the Next Meeting (April):
  Agree on conclusions
  Agree on WID
  Sent TR for Approval
Overall Plan:
  See dedicated slide
Risks:
  Tight schedule if not scheduled on the agenda in upcoming meetings