## Slide 1: SA WG3 Status report for FS_eNPN_Ph2_SEC
Christine Jost
Ericsson

## Slide 2
Key Issues | Solutions | Solution status
Security of non-3GPP access for SNPN | Nine solutions, mostly on trusted and untrusted non-3GPP access | Only one has evaluation without Editor’s Note
Authentication for UE access to hosting network | Four solutions | None has evaluation without Editor’s Note
TR 33.858 Summary
FS_eNPN_Ph2_SEC Status
SA3#108-bis-e Oct 10-14, 2022
Deadline to introduce new Key Issues
SA3#109
Nov 14-18, 2022
Conclusions
SA3#109-bis
Jan 16-20, 2023
Conclusions
WID
SA3#110
Feb 20-24, 2023
Normative work

## Slide 3
January meeting:
  Conclusions
  WID
    If WIDs are not in scope of the meeting, start discussing the WID as contribution “for discussion”
February meeting:
  Normative work
  If WIDs are not in scope of the January meeting, formally agree on WID
Overall plan
FS_eNPN_Ph2_SEC Status

## Slide 4
General
  TR 33.858 v0.3.0 contains two key issues and 13 solutions
Dependencies:
  SA2 study FS_eNPN_Ph2, TR 23.700-08 v1.4.0, completion rate 98%
    Key issue #1 on mobility between SNPNs: conclusions finalized
    Key issue #2 non-3GPP access for SNPNs: conclusions agreed, but normative work dependent on SA3 feedback
    Key issues #3-6 on access to localized services: conclusions agreed, but one Editor’s Note left
    Next SA2 meeting is 16-20 January 2023, so in parallel with SA3#109bis
  SA2 normative work eNPN_Ph2, completion rate 50%, target completion by Q1/2023
FS_eNPN_Ph2_SEC status after SA3#109
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960033 | Study on security aspects of enhanced support of Non-Public Networks phase 2 | FS_eNPN_Ph2_SEC | Rel-18 | S3 | Mar-2023 | 10% | 60% | TR 33.858

## Slide 5: FS_eNPN_Ph2_SEC status after SA3#109
Contentious Issue:
  None
Focus for the Next Meeting (January):
  Conclusions on both key issues (KI#1 Security of non-3GPP access for SNPN and KI#2 Authentication for UE access to hosting network )
Overall Plan:
  See dedicated slide
Risks:
  Tight schedule, since no conclusions yet and only two meetings left to conclude normative work