## Slide 1: SA WG3 Status report for ‘FS_Id_Prvc’
Alec Brusilovsky
Interdigital

## Slide 2
Status after November:
  KI#1 is fully agreed with modifications
  KI#2 is agreed with EN that has to be cleared
  10 new solutions from seven companies agreed with modifications for inclusion in the TR Two new KIs were proposed at the July meeting with one of them (KI #2) requiring further work.
    At SA3#109, seven solution updates submitted but only six opened and only four approved
  Two solutions for KI#2 and one KI#2 modification submitted for SA3#109
    None were opened
Overall plan:
  In the January ‘23 meeting:
    concentrate on KI #1 solutions updates, evaluations, and begin concluding.
    modify KI#2 and review solutions for KI#2
  In February ‘23 meeting, conclude for KI#1 and finish evaluations for solutions for KI #2.
  Prior to the February meeting have the following treatment for KI #1 and KI #2
    in the last week of January, a moderated email discussion and a conference call where we can exchange on the Evaluation of the solutions and on the road to conclusions.
Overall plan
‘FS_Id_Prvc Status

## Slide 3
Key Issues | Solutions | Solution status
TR Summary
‘FS_Id_Prvc’ Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues and Solution proposals
SA3#108
Aug 22-26, 2022
Refining of Key Issues and solutions
SA3#108 Adhoc-e Oct 10-14, 2022
Refining solutions
SA3#109
Nov 14-18, 2022
Evaluations for KI #1 solutions
KI #1
KI #2
Ten proposed solutions
for KI #1
2 proposed solutions
for KI #2
SA3#109 Adhoc-e
Jan 14-18, 2023
Refining evaluations
Conclusions
SA3#110
Feb 20-24, 2023
Refining Conclusions

## Slide 4
General
Dependencies:
  Some (the SID may have RAN impacts)
‘FS_Id_Prvc’ status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
940016 | Study on Standardising Automated Certificate Management in SBA | FS_Id_Prvc | Rel-18 | S3 | Mar-2023 | 10 | 12 | TR 33.870

## Slide 5: ‘FS_Id_Prvc’ status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  May be for RAN (KI #2) and none determined yet for SA2
Contentious Issue:
  No current technical contentious issues and only stemming from “absolute consensus” at the e-meetings
Focus for the Next Meeting :
  Finalise solutions
  Finalise evaluations
  Start conclusions
Overall Plan:
  See dedicated slide
Risks:
  SI completion in Q1 2023 (due to the lack of time