## Slide 1: SA WG3 Status report for FS_5WWC_Ph2_Sec
Saurabh Khare
Nokia, Nokia Shanghai Bell

## Slide 2
August meeting:
  Add solutions for current key issues KIs.
October meeting:
  Add new KIs and
  Concentrate on solution update and conclusion.
November meeting:
  Add new KIs and
  Concentrate on solution update and conclusion.
January meeting:
  Concentrate on solution update and conclusion.
  Conclude pending KIs
  Agree on WID draft
  The TR is expected to sent for information.
February meeting:
  Start normative work
  Additional conclusion in TR may also be added. The TR is expected to be sent for approval.
  Agree on the WID
April and May meeting:
  Normative work
Overall plan
FS_5WWC_Ph2_Sec Status

## Slide 3
TR Summary
FS_5WWC_Ph2_Sec Status
SA3#107 Adhoc-e Jun27-July1st 2022
TR scope & skeleton and Key Issues proposals
SA3#108
Aug 22-26, 2022
new Key Issues and solutions
SA3#108 Adhoc-e Oct 10-14, 2022
new KI+solution proposals
SA3#109
Nov 14-18, 2022
New KI and solutions introduced
Conclusion is added
Key Issues | Solutions | Solution status
#1: Authentication of AUN3 device behind RG and supporting EAP | Solution #1 EAP_AKA prime based authentication for AUN3 devices Solution #2 EAP base authentication for AUN3 devices behind RG in PLMN Solution #3 EAP base authentication for AUN3 devices behind RG in SNPN Solution #4 EAP base authentication for AUN3 devices behind RG in SNPN by AAA server | Agreed and concluded with EN Solution #2 is used as the basis for PLMN Solution #3 and #4 are used as the basis for SNPN.
#2: Security aspect of slice information exposure of N3IWF/TNGF to UE |  | Due to SA2 progress on the issues, there is no normative work needed for this KI
#3: Security aspect of slice information exposure of N3IWF/TNGF | Presented but postponed | 
Key issue #4: Security aspect of TNAP mobility without full authentication | Solution #5: TNAP mobility solution with rand Solution #6: TNAP mobility solution with count Solution #7: Using Fast BSS Transition for TNAP mobility Solution #8: Security Establishment for TNAP Mobility | 
SA3#109 Adhoc-e
Jan 16-20, 2023
Solution completion
Pending KIs
Conclusions
SA3#110
Feb 20-25, 2023
No new KI allowed
Solution completion and
Conclusions

## Slide 4
FS_5WWC_Ph2_Sec status after SA3#109
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960030 | Study on Security aspects for 5WWC Phase 2 | FS_5WWC_Ph2_Sec | Rel-18 | S3 | Mar-2023 | 30% | 60% | TR 33.887 is updated for: 1 new KI and related solutions are added(TNAP). Existing solutions are updated for KI1 and related conclusion is also added
General
  TR 33.887 v0.4.0 contains 4 key issues and related solutions
Dependencies:
  SA2 is waiting for the BBF/CableLabs LS response and has not concluded their all KIs.

## Slide 5
FS_5WWC_Ph2_Sec status after SA3#109
  SA2/RAN impacts and dependencies:
  SA2 is waiting for the BBF/CableLabs LS response and has not concluded their all KIs.
  None for RAN.
Contentious Issue:
  None
Focus for the Next Meeting :
  Update solutions for KI4 and try to conclude KI4
  Add postponed KIs and solutions
Overall Plan:
  See dedicated slide
Risks: