## Slide 1: SA WG3 Status report for FS_MBS_SEC_Ph2
Longhua Guo
Huawei

## Slide 2
In August meeting:
  Concentrate on key issues (new and updated).
  Solutions are also welcome.
In October meeting:
  Concentrate on solutions (new and updated).
  New key issues are not expected after October meeting . (However, considering the timeline of RAN group, RAN-related new key issue is also welcome if any.)
In November meeting:
  Concentrate on solution update and conclusion.
  The TR is expected to sent for information.
In January meeting:
  Concentrate on solution update and conclusion.
In February meeting:
  Additional conclusion in TR may also be added. The TR is expected to be sent for approval
  WID proposal is planned to be submitted for approval.
In April & May meeting:
  Normative work
Overall plan
FS_MBS_SEC_Ph2 Status

## Slide 3
Key Issues | Solutions | Solution status
Handling in MOCN | None | None
TMGI protection | 3 solutions | With editor’s notes
TR Summary
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues proposals
SA3#108
Aug 22-26, 2022
Key Issues proposals
New solutions
SA3#109 Nov 14-18, 2022
New solutions
Solution update
Conclusions
SA3#110 Jan 16-20, 2023
New solutions
Solution update
Conclusions
FS_MBS_SEC_Ph2 Status
SA3#108ad
Aug 22-26, 2022
Key Issues proposals
New solutions

## Slide 4
General
  TR 33.883 v0.4.0 contains two key issues (handling in MOCN and TMGI protection) and three solutions.
Dependencies:
  SA2 SID (Study on architectural enhancements for 5G multicast-broadcast services Phase 2)
    Several conclusions in SI were agreed
    Normative work is already started
  RAN WID (Enhancements of NR Multicast and Broadcast Services)
    Normative work is already started
FS_MBS_SEC_Ph2 status after SA3#108-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960041 | Study on security enhancements for 5G multicast-broadcast services Phase 2 | FS_5MBS_SEC_Ph2 | Rel-18 | S3 | Mar-2023 | 30% | 50% | TR 33.883

## Slide 5
Contentious Issue:
  Handling in MOCN
  TMGI protection
Focus for the Next Meeting :
  Update to existing solutions
  New solution with minor system impact
  Conclusion to the key issues
Overall Plan:
  See dedicated slide
Risks:
  No conclusion was agreed at SA3 #109 meeting.
FS_MBS_SEC_Ph2 status after SA3#109