## Slide 1: SA WG3 Work Plan for FS_AIML
Marcus Wong
OPPO

## Slide 2
October meeting
  Potential CC before meeting to discuss way forward
  Continue key issue discussion, make progress to have initial KI agreements
  Possible potential evaluation(s) based on agreed KI
November meeting
  Continue KI and solution discussions
  Start solution evaluations
  First conclusions
  Discussion on potential WID objectives. Preliminary agreements on objectives.
January meeting/February
  Conclusions for all key issues and solutions
  Potential WID agreement
  Potential normative work
April meeting
  Potential normative work
May meeting
  Finalize potential normative work
Overall plan
FS_AIMLStatus

## Slide 3
Key Issues | Solutions | Solution status
None so far. | None so far. | N/A
TR 33.898 Summary
FS_AIML Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Skeleton and Scope
Key Issues and Solution proposals
SA3#108
Aug 22-26, 2022
Nothing happened
SA3#108 Adhoc-e Oct 10-14, 2022
introduce new Key Issues
Potential Solution
SA3#109
Nov 14-18, 2022
KI and Solutions
Initial conclusions & WID

## Slide 4
General
  TR 33.898 v0.1.0 contains the scope and background clauses.
Dependencies:
  SA2 has 7 stable KI identified including several with security dependencies identified (KI#2, 3, 4, 5)
  SA2 has 47 solutions captured in TR 23.700-80, 18 impacting KI with security dependencies.
  SA2’s KI#3 has interim conclusion, TR sent to SA#97 for information.
  User consent and privacy aspect of the FS_AIML are to be coordinated with both FS_UC3S_Ph2 and FS_Id_Prvc studies
  Awaiting reply LS on Network Information Exposure to UE from SA3.
  SA2 and SA3 has full overlap October and November.
FS_AIML status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960037 | Study on the security and privacy of AI/ML-based services and applications in 5G | FS_AIML | Rel-18 | S3 | Mar-2023 | 0 | 5% | TR 33.898

## Slide 5: FS_AIML status after SA3#108-e
  No progress in SA3#108-e as agenda was excluded
  SA2/RAN impacts and dependencies:
  None for RAN
  SA2 sent TR to SA#97 for information, 4 KI with SA3 impact, 1 KI with interim conclusion
Contentious Issue:
  TBD.
Focus for the Next Meeting :
  First key issue agreements
Overall Plan:
  See dedicated slide
Risks:
  One or more company/companies continue blocking progress of KI discussion and conclusion.
  If no progress with KI and/or solution can be made in the next meeting, FS_AIML schedule may be severely jeopardized.