## Slide 1: Status report for FS_eNS_Ph3 after SA3 #108-e
Zander Lei
Huawei

## Slide 2
Overall Plan (updated)
May meeting
  SID approval
July meeting
  Approval of Skeleton and Scope of TR 33.886
  Proposals for new Key Issues
August meeting
  Concentrate on key issues (new and updated)
  New solutions are welcomed
October meeting
  Key issues and solutions
November meeting
  Concentrate on solutions
  Early conclusions and WID proposals
  new key issues are not expected
January meeting
  Normative text proposal (if WID approved)
  Solutions and Key Issue conclusions
February meeting
  New conclusions and revised WID (if needed)
  Normative text proposal and updates
  TR completed and sent for approval

## Slide 3
General
  All 7 proposals on new/updating key issue were noted (Reasons: waiting for SA2 conclusions)
  All 3 solutions were all noted (Reasons: waiting for SA2 conclusions)
Dependencies:
  SA2’s work on FS_eNS_Ph3
    TR 23.700-041 v0.3.0, completion rate 50%, end date Dec-2022
    6 key issues and 37 solutions have been agreed
    To update based on SA2 August meeting(concurrent)
FS_eNS_Ph3 status after SA3#108-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960029 | Study on enhanced security for network slicing Phase 3 | FS_eNS_Ph3 | Rel-18 | S3 | Mar-2023 | 15% | 15% | No change to TR 33.886
Key Issues | KI status | Solutions | Solution status
#1 : providing VPLMN slice information to roaming UE | Incomplete: missing security threats and requirements | Nil | NA
#2 : temporary slice authorization and slice service area authorization | ok | Nil | NA
#3: network slice admission control (NSAC) | Incomplete: missing security threats and requirements | Nil | NA

## Slide 4: FS_eNS_Ph3 status after SA3#108-e
  SA2 impacts and dependencies:
  Conclusions/evaluations of solutions in SA2
Contentious Issues:
  Whether to progress KIs only after SA2’s conclusions
Discussions arising from Contenious Issues:
  SA3 meetings should be arranged after SA2’s (avoid concurrent meetings)
  If “progressing KIs only after SA2’s conclusions” is recommended practice, propose to
    request from SA for more time (e.g. 2 quarter lag)
    only approve SID when SA2 is approaching conclusions
Focus for the Next Meeting :
  Completing most, if not all, key issues
Overall Plan:
  See pg2
Risks:
  Progress delayed