## Slide 1: SA WG3 Status report for ‘FS_Id_Prvc’
Alec Brusilovsky
Interdigital
Changes from July 2022 version are highlighted.

## Slide 2
Status after July:
  Six new solutions from four companies were already presented and tentatively agreed with modifications for inclusion in the TR but noted by a single company at July meeting. All six solutions for KI#1 postponed. KI#1 with ENs.
  Two new Kis were proposed at the July meeting with one of them (KI #2) requiring further work.
  New KI#2 threat and requirement to be further discussed
Overall plan:
  In the August ‘22 meeting: concentrate on KI #1 (e.g., update and agree).
  In October ‘22 meeting: concentrate on KI #1 (e.g., update and agree) and further develop solutions for KI #1 towards completion of their evaluation. Finalize all solutions for KI #1 and start the conclusions process for KI #1. Also in October, advance solutions for KI #2
  In November meeting conclude on KI #1, start the evaluation of solutions for KI #2
  Prior to the November meeting have the following treatment for KI #1 and KI #2
    in the last week of October, a moderated email discussion
    In the first week of November, a conference call where we can exchange on the Evaluation of the solutions and on the road to conclusions
Overall plan
‘FS_Id_Prvc Status

## Slide 3
Key Issues | Solutions | Solution status
TR Summary
‘FS_Id_Prvc’ Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues and Solution proposals
SA3#108
Aug 22-26, 2022
Refining of Key Issues and solutions
SA3#108 Adhoc-e Oct 10-14, 2022
Refining solutions
SA3#109
Nov 14-18, 2022
Conclusions for solutions
KI #1
KI #2
Six proposed solutions
for KI #1

## Slide 4
General
Dependencies:
  Some (the SID may have RAN impacts)
‘FS_Id_Prvc’ status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
940016 | Study on Standardising Automated Certificate Management in SBA | FS_Id_Prvc | Rel-18 | S3 | Mar-2023 | 10 | 12 | TR 33.870

## Slide 5: ‘FS_Id_Prvc’ status after SA3#107-e (last discussion at SA3#107Adhoc-e)
  SA2/RAN impacts and dependencies:
  May be for RAN (KI #2) and none determined yet for SA2
Contentious Issue:
  No current technical contentious issues and only stemming from “absolute consensus”
Focus for the Next Meeting :
  Break through the contention issues in October
Overall Plan:
  See dedicated slide
Risks:
  Risk of slipping solutions into November meeting due solutions treated at the same time as KI#1 in October meeting.
  SI completion in Q1 2023 (due to the “absolute consensus” requirement