## Slide 1: SA WG3 Status report for FS_UC3S_Ph2
Rong Wu
Huawei

## Slide 2
In August meeting:
  Concentrate on key issues (new and updated).
  Solutions are also welcome.
In October meeting:
  Concentrate on key issues (new and updated).
  New key issues are not expected after October meeting.
In November meeting:
  Concentrate on solution update and conclusion.
  The TR is expected to be sent for information.
  WID proposal is planned to be submitted for discussion and approval.
In January/February meeting:
  Start normative work.
  Additional conclusion in TR may be also added. The TR is expected to be sent for approval.
In April meeting:
  Continue the normative work
In May meeting:
  Finalize normative work
Overall plan
FS_UC3S_Ph2 Status

## Slide 3
Key Issues | Solutions | Solution status
User consent handling for eNA roaming | None | None
User consent handling for NTN(without security requirements) | None | None
TR Summary
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues proposals
SA3#108
Aug 22-26, 2022
Key Issues proposals
New solutions
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
New solutions
SA3#109
Nov 14-18, 2022
Conclusions
WID proposal
FS_UC3S_Ph2 Status

## Slide 4
General
  TR 33.896 v0.1.0 contains scope and two key issues (user consent handling in NTN and eNA roaming case). The requirements for the NTN key issues are to be added.
Dependencies:
  SA2 eNA SID (Study of Enablers for Network Automation for 5G System (5GS); Phase 3)
    Solutions available to all key issues
    No conclusions so far
  SA2 MEC SID (5G System Enhancements for Edge Computing; Phase 2)
    Solutions available to all key issues
    No conclusions so far
  RAN3 RAN AI/ML WID (Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN)
    TR has concluded.
    TS is not started yet.
  NOTE: NTN user consent is for R17 NTN, SA2 and RAN will adopt the conclusion of user consent.
FS_UC3S_Ph2 status after SA3#108-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960039 | Study of Security aspects on User Consent for 3GPP Services Phase 2 | FS_UC3S_Ph2 | Rel-18 | S3 | Mar-2023 | 0% | 10% | TR 33.896

## Slide 5
Contentious Issue:
  User consent handling in eNA roaming case
  User consent handling in MEC roaming case
  User consent handling in NTN case
Focus for the Next Meeting :
  concentrate on key issues (new and updated). The requirements for the existing key issues are expected to reach consensus.
  Solutions are also welcome.
Overall Plan:
  See dedicated slide, i.e. slide 2
Risks:
  There is no progress at SA3 #108e meeting as one company objected all the KIs. And the security work may have RAN and SA2 impact and dependency. If the key issues related to RAN and SA2 WIDs are proposed late, there will be risk for TR completion in Q4 2022 (e.g. due to confirmation required but late feedback from RAN and SA2 group).
FS_UC3S_Ph2 status after SA3#108-e