## Slide 1: SA WG3 Status report for FS_5G_ProSe_Ph2
Wei Zhou
CATT

## Slide 2
August meeting (SA3#108-e, Aug 22-26 , 2022):
  Add key issues
  Add solutions for existing key issues
October meeting (SA3#108-bis-e, Oct 10-14, 2022):
  Last meeting to add key issues
  Add solutions for existing key issues
  Solution evaluations
November meeting (SA3#109, Nov 14-18 , 2022):
  Last meeting to add solutions
  Solution evaluations
  Conclusions for key issues
  Agree on WID
January meeting (SA3#109Bis, Jan 16-20 , 2023):
  Start normative work
  Conclusions for key issues
February meeting (SA3#110, Feb20-24 , 2023):
  Normative work
April meeting (110Bis, Ap17-21 , 2023):
  Finalize normative work
May meeting (SA3#111, May22-26 , 2023):
Overall plan
FS_5G_ProSe_Ph2 Status

## Slide 3
Key Issues | Solutions | Solution status
Key Issue #1: Security for UE-to-UE Relay discovery | Solution #1, Solution #8, Solution #9 | 
Key Issue #2: Security of UE-to-UE Relay | Solution #3, Solution #4, Solution #5, Solution #6, Solution #7, Solution #10 | 
Key issue #3: Authorization in the UE-to-UE Relay Scenario | Solution #1, Solution #3, Solution #4, Solution #5, Solution #10 | 
Key Issue #4: Privacy of information over the UE-to-UE Relay | Solution #2 | 
TR 33.740 Summary
FS_5G_ProSe_Ph2 Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues
SA3#108
Aug 22-26, 2022
Key Issues and Solution proposals
SA3#108-bis-e
Oct 10-14, 2022
Deadline to introduce new Key Issues
SA3#109
Nov 14-18, 2022
Conclusions
SA3#109Bis
Jan 16-20 , 2023
Conclusions

## Slide 4
General
  TR 33.740 v0.2.0 contains scope, 4 key issues , 10 solutions
Dependencies:
  SA2’s work on FS_5G_ProSe_Ph2, TR 23.700-33
FS_5G_ProSe_Ph2 status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
950024 | Study on Security Aspects of Proximity Based Services in 5GS Phase 2 | FS_5G_ProSe_Ph2 | Rel-18 | S3 | Mar-2023 | 15% | 40% | TR 33.740

## Slide 5: FS_5G_ProSe_Ph2 status after SA3#107Adhoc-e
  SA2/RAN impacts and dependencies:
  None for RAN and none determined yet for SA2
Contentious Issue:
  None
Focus for the Next Meeting :
  Add new key issues
  Add solutions for existing key issues and new approved key issues
Overall Plan:
  See dedicated slide
Risks:
  None