## Slide 1: SA WG3 Status report for FS_MBS_SEC_Ph2
Longhua Guo
Huawei

## Slide 2
In August meeting:
  Concentrate on key issues (new and updated).
  Solutions are also welcome.
In October meeting:
  Concentrate on solutions (new and updated).
  New key issues are not expected after October meeting . (However, considering the timeline of RAN group, RAN-related new key issue is also welcome if any.)
In November meeting:
  Concentrate on solution update and conclusion.
  The TR is expected to sent for information.
  WID proposal is planned to be submitted for discussion and approval.
In January/February meeting:
  Start normative work.
  Additional conclusion in TR may also be added. The TR is expected to be sent for approval
In April meeting:
  Continue the normative work
In May meeting:
  Finalize normative work
Overall plan
FS_MBS_SEC_Ph2 Status

## Slide 3
Key Issues | Solutions | Solution status
Handling in MOCN (without threat and requirement) | None | None
TMGI protection(without requirement) | None | None
TR Summary
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues proposals
SA3#108
Aug 22-26, 2022
Key Issues proposals
New solutions
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
New solutions
SA3#109 Nov 14-18, 2022
Conclusions
WID proposal
FS_MBS_SEC_Ph2 Status

## Slide 4
General
  TR 33.883 v0.3.0 contains scope and two key issues (handling in MOCN and TMGI protection). The requirements for the key issues are to be added.
Dependencies:
  SA2 SID (Study on architectural enhancements for 5G multicast-broadcast services Phase 2)
    Solutions available to all key issues
    Several conclusions were agreed
  RAN WID (Enhancements of NR Multicast and Broadcast Services)
    Normative work is already started
FS_MBS_SEC_Ph2 status after SA3#108-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960041 | Study on security enhancements for 5G multicast-broadcast services Phase 2 | FS_5MBS_SEC_Ph2 | Rel-18 | S3 | Mar-2023 | 0% | 12% | TR 33.883

## Slide 5
Contentious Issue:
  Handling in MOCN
  TMGI protection
Focus for the Next Meeting :
  concentrate on key issues (new and updated). The requirements for the existing key issues are expected to reach consensus
  Solutions are also welcome.
Overall Plan:
  See dedicated slide
Risks:
  There is no progress at SA3 #108e meeting.
  The security work has RAN impact and dependency. If the key issues related to RAN WID is proposed late, there will be risk for TR completion in Q4 2022 (e.g. due to confirmation required but late feedback from RAN group)
FS_MBS_SEC_Ph2 status after SA3#108-e