## Slide 1: SA WG3 Status report for ‘FS_5G_Femto_Sec’
Peilin Liu (ZTE)
Hua Song (China Mobile)

## Slide 2
Overall plan
‘FS_5G_Femto_Sec’ overall plan
Meeting | Plans | SID TU | WID TU
SA3#115ah-e (April), finished | TR skeleton, assumptions and new KIs are approved | 0.5 | 
SA3#116 (May), finished | New solutions and KI updates are approved | 0.5 | 
SA3#117 (August) | New solutions, solution updates and evaluations | 0.5 | 
SA3#118 (October) | Solution updates, evaluaitons and start conclusion work | 0.5 | 
SA3#119 (November) | Finalise SID conclusions Corresponding WID proposal | 0.5 | 
SA#106 (December) | Send TR to SA for information and for approval |  | 
Prior to SA3#120 | Potentially offline session to accelerate normative work progress Offlist email discussions for prepared CRs |  | 
SA3#120 (Feb 2025) | Normative work |  | 0.75
Between SA3#120 and #121 | Offline sessions and offlist email discussions |  | 
SA3#121 (April 2025) | Finalise the Normative work |  | 0.75
TUs planned: 4

## Slide 3
General
  TR 33.745 v0.3.0 contains 9 key issues and 11 solutions
Dependencies:
  SA2’s work on FS_5G_Femto, TR 23.700-45
  RAN3’s work on FS_NR_WAB_5GFemto, TR 38.799
Contentious Issue:
  None identified
Risks:
  None identified
‘FS_5G_Femto_Sec’ status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030028 | Study on security aspects of 5G Next Radio (NR) Femto | FS_5G_Femto_Sec | Rel-19 | S3 | Dec-2024 | 30% | 60% | TR 33.745

## Slide 4
Pending issues
  Solutions to new KI#9
  EN resolve and evaluations to solutions
  Agreement on the conclusions for the KIs
TUs consumed
  SA3#115-adhoc-e - 0.5TU
  SA3#116 - 0.5TU
  SA3#117 - 0.5TU
TUs remaining
  SA3#118 – 0.5
  SA3#119 – 0.5
Plan for completion
  SA3#119 Finalise the SID, send TR for information and approval
  SA3#121 Finalise the Normative text
‘FS_5G_Femto_Sec’ pending work and plan for completion