## Slide 1: SA WG3 Status report for FS_UIA_Sec
Samir Ferdi
Interdigital

## Slide 2
TUs planned: 6
In SA3#115-adhoc-e meeting:
  Get KIs agreed
In SA3#116 meeting:
  Add solutions
  Last meeting to add KIs
In SA3#117 meeting :
  Clear ENs in solutions
  Add solution evaluations
  Last meeting to add solutions
In SA3#118 meeting :
  Add conclusions and complete evaluations
  Initial WID proposal
In SA3#119 meeting :
  Complete conclusions
  Send TR for information & approval
  WID proposal
Overall plan
FS_UIA_Sec overall plan

## Slide 3
General
  TR scope in, stable security and architecture assumptions
  3 key issues in the TR for user A&A (KI#1), user id privacy (KI#2), device A&A (KI#3).
  27 solutions (5 new) in the TR (KI#1 : 16, KI#2 : 11, KI#3 : 4)
  Partial conclusion for KI#3 (authentication only, authorization is FFS).
Dependencies:
  SA2 study FS_UIA_ARC conclusions.
Contentious Issue:
  No agreement to align with SA2 majority view of using NAS based mechanism for user authentication (Question 1a in S3-243558).
  No agreement whether there is a privacy issue with SMS/IMS services provided to a UE when a user identifier is active with the UE subscription (Question 2 in S3-243558).
Risks:
  Inability to conclude KI#1 without agreement on user authentication mechanism.
FS_UIA_Sec status after SA3#117
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030032 | Study on security aspects of User Identities and Authentication | FS_UIA_Sec | Rel-19 | S3 | Nov-2024 | 35% | 65% | TR 33.700-32 V0.3.0

## Slide 4
Pending issues
  Finalize solution evaluations.
  Finalize KI#3 conclusion (authorization).
  Add conclusions for KI#1 and KI#2.
Dependencies:
  SA2 study FS_UIA_ARC conclusions (TR 23.700-32 , KI#1 and KI#2).
TUs consumed
  SA3#115-adhoc-e : 0.5
  SA3#116 : 1
  SA3#117 : 2
TUs remaining
  1 TU for SA3#118 and SA3#119
Plan for completion
  SA3#119 conclude study, send TR for information and approval
  SA3#121 conclude normative work
FS_UIA_Sec pending work and plan for completion