## Slide 1: SA WG3 Status report for ‘FS_Metaverse_Sec’
Rohini Rajendran (Samsung)
Lihui Xiong (OPPO)

## Slide 2
TUs planned
In SA3#115 Adhoc e-meeting:
  2 KIs agreed
In SA3#116 meeting:
  1 solution agreed
In SA3#117 meeting:
  2 new Key issues approved (expect no more KI in further meeting)
  2 new solutions (for KI#1) and 1 new solution (for KI#2) were approved
In SA3#118 meeting:
  Solution and evaluation to all solutions are expected
In SA3#119 meeting:
  Key issue#1 concluded.
  Key issue#2 partially concluded.
  WID proposal approved.
In SA3#120 meeting:
  Based on agenda plan is to evaluate all solutions in the study in Ad-hoc e-meeting or complete the conclusion during SA3#120 meeting.
  Send TR for approval
  Start WID work.
In SA3#121 meeting
  Finalise WID work
Overall plan
‘FS_Metaverse_Sec’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative)
WT1 | 1.5 | 0.5
WT2 | 1.5 | 0.5
WT3 | 1 | 1

## Slide 3
General
  TR 33.721 v0.3.0 contains 4 key issues and 10 solutions.
  Key issue#1 is concluded and Key issue#2 is partially concluded
  Key issue#3 and Key issue#4 is yet to be concluded
Dependencies:
  None
Contentious Issue:
  None
Risks:
  Completing the normative work within timeline
‘‘FS_Metaverse_Sec‘‘ status after SA3#119
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030039 | Study on security aspects of 5G mobile metaverse services | ‘FS_Metaverse_Sec | Rel-19 | S3 | Mar-2025 | 50% | 70% | -

## Slide 4
Pending issues
  Conclusion for below key issues
    Issue#1: Authentication and authorization of digital representation
    Issue#2: Security aspects of digital asset container in 5G
    Issue#3: Privacy of user sensitive information (reuse of user consent framework defined in TS 33.501 is FFS)
Dependencies:
  None
TUs consumed
  SA3#115 Adhoc-e - 0.5 TU
  SA3#116 - 0.25 TU
  SA3#117 - 0.5 TU
  SA3#118 – 0.5 TU
  SA3#119 – 0.5 TU
TUs remaining
  SA3#120 - 1 TU
Plan for completion
  Study exceeded the planned completion deadline.
  SA3#120 (study completion and Send TR for approval)
  SA3#121 Finalise the WID
‘‘FS_Metaverse_Sec‘‘ pending work and plan for completion