## Slide 1: SA WG3 Status report for UAS3
Markus Hanhisalo
Ericsson

## Slide 2
TUs planned
  Total TU estimates for the study phase: 1.5
  Total TU estimates for the normative phase: 1.5
  Total TU estimates: 3
In SA3#115Ad-hoc meeting:
  One KI approved
In SA3#116 meeting
  4 KI1 solutions were approved
In SA3#117 meeting
  2 KI1 solutions were approved
  Evaluations approved
In SA3#118 meeting
  1 new solution was approved (S3-244426)
  Evaluations approved (S3-244380, S3-244381)
  KI1 was concluded (S3-244427)
  TR 33.759 0.4.0 (S3-243830)
In SA3#119 meeting
  2 new solutions were approved (S3-245256, S3-245257) and one solution update (S3-244842)
  TR 33.759 0.5.0 (S3-245194) was sent to TSG for information and approval
  The WID on UAS security enhancements (S3-245321) was agreed in SA3#119
In SA3#120 meeting
  9 CR contributions but no agreement for the normative CR
  The plan is to finish work in SA3#121 in Goteborg
Overall plan
UAS3 overall plan

## Slide 3
General
  TR scope has been set
  TR overview and security assumptions have been set
  Key Issue for security enhancements to NEF services in support of multiple USSs has been set
  7 solutions agreed, one new solutions was agreed in SA3#118 (S3-244426)
  Evaluations agreed (S3-244380, S3-244381)
  Conclusion agreed (S3-244427)
Dependencies:
  SA2’s study work on UAS TR 23.700-59
Contentious Issue:
  None
Risks:
  None identified
UAS3 status after SA3#118
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030033 | Security of Uncrewed Aerial Systems (UAS) Phase 3 | FS_UAS_Ph3_Sec | Rel-19 | S3 | Mar-2024 | 50% | 100% | pCRs to TR 33.759

## Slide 4
General
  TR is ready and completed, it has one key issue, 9 solutions and it has been concluded
  It has one Key Issue for security enhancements to NEF services in support of multiple USSs
  9 solutions, two new solutions were approved in SA3#119 (S3-245256, S3-245257) and one solution update (S3-244842)
  Evaluations are done
  Editor’s Notes were changed to Notes
  Conclusion was approved in SA3#118 meeting (S3-244427)
  Presentation of Report to TSG: TR 33.759 'Study on security enhancements of Uncrewed Aerial Systems (UAS) Phase 3', Version 1.0.0 (S3-245370) was approved
Dependencies:
  SA2’s study work on UAS TR 23.700-59
Contentious Issue:
  None
Risks:
  None identified
UAS3 status after SA3#119
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030033 | Security of Uncrewed Aerial Systems (UAS) Phase 3 | FS_UAS_Ph3_Sec | Rel-19 | S3 | Mar-2024 | 100% | % | pCRs to TR 33.759

## Slide 5
General
  Normative work started at SA3#120. There were 9 CR proposals for the normative work. Only one CR was agreed at the SA3#120 meeting.
  The plan is to finish the normative work at the next SA3#121 meeting in Goteborg.
  Exception sheet was sent to SA March plenary (S3-251165). New expected completion date is June 2025.
Dependencies:
  SA2’s work item on UAS TS 23.256
Contentious Issue:
  In USS changeover procedure during a UAV flight from USS1 to USS2, who triggers the UUAA, is it UAV or USS2 and is it UUAA or re-auth that is triggered (TS 23.256 clause 5.13.2, step 20).
Risks:
  None identified
UAS3 status after SA3#120
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030033 | Security of Uncrewed Aerial Systems (UAS) Phase 3 | FS_UAS_Ph3_Sec | Rel-19 | S3 | Mar-2025 | 100% | % | TR 33.759
1060058 | Security of Uncrewed Aerial System Phase 3 | UAS_Ph3_Sec | Rel-19 | S3 | Mar-2025 | 0% | 5% | CR to TS 33.256

## Slide 6
Pending issues
  In USS changeover procedure during a UAV flight from USS1 to USS2, who triggers the UUAA, is it UAV or USS2 and is it UUAA or re-auth that is triggered (TS 23.256 clause 5.13.2, step 20).
Dependencies:
  SA2’s work on UAS TS 23.256
TUs consumed
  SA3#120 – 0,5
TUs remaining
  SA3#120 – 1
Plan for completion
  The plan is to do the normative work at the next SA3#121 meeting in Goteborg in April 2025. New expected completion date is June 2025.
UAS3 pending work and plan for completion