## Slide 1: SA WG3 Status report for ‘5G_Femto_Sec’
Peilin Liu (ZTE)
Hua Song (China Mobile)

## Slide 2
Overall plan
‘FS_5G_Femto_Sec’ overall plan
Meeting | Plans | SID TU | WID TU
SA3#115ah-e (April), finished | TR skeleton, assumptions and new KIs are approved | 0.5 | 
SA3#116 (May), finished | New solutions and KI updates are approved | 0.5 | 
SA3#117 (August) | New solutions, solution updates and evaluations | 0.5 | 
SA3#118 (October) | Solution updates, evaluaitons and start conclusion work | 0.5 | 
SA3#119 (November) | Finalise SID conclusions Corresponding WID proposal | 0.5 | 
SA#106 (December) | Send TR to SA for information and for approval |  | 
Prior to SA3#120 | Potentially offline session to accelerate normative work progress Offlist email discussions for prepared CRs |  | 
SA3#120 (Feb 2025) | Normative work |  | 0.5
Between SA3#120 and #121 | Offline sessions and offlist email discussions |  | 
SA3#121 (April 2025) | Normative work |  | 0.5
SA3#122 (May 2025) | Finalise the Normative work |  | 0.5
TUs planned: 4

## Slide 3
General
  TS 33.545 v0.1.0 specifies the security requirements, procedures and features for NR Femto subsystem
  The normative work is completed
Dependencies:
  SA2’s work on System aspects of 5G NR Femto
  RAN3’s work on Additional topological enhancements for NR
Contentious Issue:
  None identified
Risks:
  None identified
‘FS_5G_Femto_Sec’ status after SA3#119
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1060062 | Security aspects of Next Radio (NR) Femto | 5G_Femto_Sec | Rel-19 | S3 | March-2025 | 0% | 100% | TS 33.545

## Slide 4
Pending issues
  None identified
TUs consumed
  SA3#115-adhoc-e - 0.5TU
  SA3#116 - 0.5TU
  SA3#117 - 0.5TU
  SA3#118 - 0.5TU
  SA3#119 - 0.5TU
  Normative work:
  SA3#120 - 0.5TU
TUs remaining
  The normative work is completed
Plan for completion
  SA#107 send TS for information and approval
‘5G_Femto_Sec’ pending work and plan for completion