## Slide 1: SA WG3 Status Report for ACME_SBA
Charles Eckel, Cisco Systems

## Slide 2
ACME_SBA Overall Plan
Meeting | Plans | SID TU | WID TU
SA3#115 (Feb 2024) | Initial version of TR 33.776 with introduction, scope, and five key issues | 0.5 | 
SA3#116 (May 2024) | Two new key issues, solutions for several key issues, and initial evaluations for a few key issues | 0.5 | 
SA3#117 (Aug 2024) | Solutions for all but one key issues and progress on evaluations | 0.5 | 
SA3#118 (Oct 2024) | Solution for remaining key issues, additional solutions and evaluations, start of conclusions | 0.5 | 
SA3#119 (Nov 2024) | Study complete and work item agreed for corresponding normative work | 0.5 | 
SA#106 (Dec 2024) | Sent TR to SA for information and for approval |  | 
SA3#120 (Feb 2025) | Normative work started, draft-CR skeleton and main content agreed |  | 0.5
SA#107 (March 2025) | Send Work Item Exception Sheet to SA for approval |  | 
SA3#121 (April 2025) | Complete normative work |  | 0.5
SA3#121 (May 2025) | Minor maintenance of normative work, if any |  | < 0.5
SA#107 (March 2025) | Send CR to SA for approval |  | 

## Slide 3
General
  Normative work started, draft-CR skeleton agreed, and main content of new informative annex agreed.
Dependencies:
  None.
Contentious Issue:
  None identified.
Risks:
  None identified.
ACME_SBA Status after SA3#120
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1060066 | WID on Automatic Certificate Management Environment (ACME) for the Service Based Architecture (SBA) | ACME_SBA | Rel-19 | S3 | Jun-2025 | 0% | 55% | Normative work going well but one more meeting needed to complete.

## Slide 4
Pending issues
  5 ENs to be addressed and some general cleanup needed to improve overall flow of information in the Annex.
  Details of mechanisms to provide authentication and authorisation at or before ACME account creation are FFS.
  New ACME identifier type needs to be listed in a new registration in the ACME Identifier Types registry and the ACME Validation Methods registry maintained by IANA.
Dependencies:
  None.
TUs consumed
  SA3#120: 0.5
TUs remaining
  SA3#121: 0.5
  SA3#122: Less than 0.5, if any
Plan for completion
  Completion of normative work at SA3#121.
ACME_SBA Pending Work and Plan for Completion