## Slide 1: SA WG3 Status report for FS_EDGE_Ph3
Ge Yao (China Unicom)
Bo Zhang (Huawei)

## Slide 2
6 TUs planned
In SA3#116 meeting:
  KI on UE info verification agreed
In SA3#117 meeting:
  All KIs and solution to be proposed.
In SA3#118 meeting:
  Solution & evaluation update
In SA3#119 meeting:
  Solution & evaluation update
  Add conclusions
In SA3#120 meeting:
  Clean up and send TR for approval
  Finalize normative work
FS_EDGE_Ph3 overall plan

## Slide 3
General
  TR 33.749 v0.6.0 contains scope, 2 key issues and 10 solutions
Dependencies:
  SA2 for system architecture, SA6 for EDGE application architecture
Contentious Issue:
  None
Risks:
  None
FS_EDGE_Ph3 status after SA3#120
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030036 | Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 | FS_EDGE_Ph3 | Rel-19 | S3 | December 2024 | 95% | 100% | Clean UP Conclusion Update

## Slide 4
Pending issues
  None
TUs consumed
  SA3#115 Adhoc-e - 0.5 TU
  SA3#116 - 0.5 TU
  SA3#117 - 0.5 TU
  SA3#118 - 0.5 TU
  SA3#119 - 0.5 TU
  SA3#120 - 0.5 TU
TUs remaining
  N/A
Plan for completion
  N/A
FS_EDGE_Ph3 pending work and plan for completion