## Slide 1: SA WG3 Status report for ‘Metaverse_Sec’
Rohini Rajendran (Samsung)
Lihui Xiong (OPPO)

## Slide 2
In SA3#120 meeting:
  Skeleton was approved in S3‑250779.
  Work Item exception was approved in S3‑251054 (to be completed by June SA#108 plenary).
  Living document on Metaverse_Sec was approved (draftCR - S3‑251166).
  WID was revised to add new Work Tasks based on concluded key issues (KI#3 & KI#4)
In SA3#121 meeting:
  Complete the security procedure for authentication and authorization of spatial localization services.
  Introduce the security procedure for authentication and authorization of digital asset services (as per conclusion of KI#3 & #4 in TR 33.721).
In SA3#122 meeting:
  Detail the security procedure for privacy exposure.
2.5 TUs planned
Overall plan
‘Metaverse_Sec’ overall plan

## Slide 3
General
  New clauses for the security of metaverse services to be introduced in TS 33.434:
    Authentication and authorization for spatial localization services
    Authentication and authorization for digital asset services
    Privacy protection for user information exposure
Dependencies:
  None
Contentious Issue:
  None
Risks:
  None
‘‘Metaverse_Sec‘‘ status after SA3#120
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1060060 | Security aspects of 5G mobile metaverse services | ‘Metaverse_Sec | Rel-19 | S3 | Mar-2025; New target – June -2025 | 0% | 35% | -

## Slide 4
Pending issues
  Procedure for the following in TS 33.434:
    Authentication and authorization for spatial localization services
    Authentication and authorization for digital asset services
    Privacy protection for user information exposure
Dependencies:
  None
TUs consumed
  SA3#120 – 0.5
TUs remaining
  SA3#121 – 1 TU
  SA3#122 – 1 TU
Plan for completion
  SA3#122 – complete the normative work
‘‘Metaverse_Sec‘‘ pending work and plan for completion