## Slide 1: SA WG3 Status report for 5GSAT_Ph3_SEC
Wei Zhou
CATT

## Slide 2
Meeting plan
  Meeting 1 (SA3#120 2025-02-17 2025-02-21 Athens, GR)
    TS skeleton + Content
  Meeting 2 (SA3#121 2025-04-07 2025-04-11 Goteborg, SE)
    TS skeleton + Content
  Meeting 3 (SA3#122 2025-05-19 2025-05-23 Fukuoka, JP)
    Content finalization
3 TUs planned
Overall plan
5GSAT_Ph3_SEC overall plan

## Slide 3
General
  TS skeleton has not been set yet.
  General content has been determined
Dependencies:
  SA2’s normative work on FS_5GSAT_Ph3 (TS 23.401)
Contentious Issue:
  Whether the security aspects specific to the Split MME and Full CN onboard deployment models should be normatively specified or in an informative manner is debated and companies have conflicting stands.
  For Split MME deployment mode, whether the solutions for threat related to DoS attacks need to be captured in specifications or not, is also contentious and debated with companies having conflicting stands.
Risks:
  None identified
5GSAT_Ph3_SEC status after SA3#120
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1060065 | Security Aspects of 5G Satellite Access Phase 3 | 5GSAT_Ph3_SEC | Rel-19 | S3 | June-2025 | 0% | 35% | TS 33.401

## Slide 4
Pending issues
  Need to set up TS skeleton.
  Need to determine normative or informative content.
  Need to determine whether DoS attack related content should be included.
Dependencies:
  SA2’s normative work on FS_5GSAT_Ph3 (TS 23.401)
TUs consumed
  1 TUs used by SA3#120
TUs remaining
  2 TUs
Plan for completion
  SA3#122
5GSAT_Ph3_SEC pending work and plan for completion