## Slide 1: SA WG3 Status report for FS_5GSAT_Ph3
Wei Zhou
CATT

## Slide 2
Meeting plan
  Meeting 1 (SA3#115 2024-02-26 2024-03-01 Athens, GR)
    TR skeleton + Key Issues
  Meeting 2 (SA3#115-adhoc-e 2024-04-15 2024-04-19 E-Meeting)
    Key Issues + Solutions
  Meeting 3 (SA3#116 2024-05-20 2024-05-24 Korea, KR)
    Solutions
  Meeting 4 (SA3#117 2024-08-19 2024-08-23 Maastricht , NL)
    Solutions + Preliminary conclusions
  Meeting 5 (SA3#118 2024-10-14 2024-10-18 India, IN)
    Solution updates + Conclusions + Preliminary WID Proposal
  Meeting 6 (SA3#119 2024-11-11 2024-11-15 Orlando , US)
    Conclusions + WID Proposal
  Meeting 7 (SA3#120 2025-02-17 2025-02-21 Athens, Greece)
    Conclusions
5 TUs planned
Overall plan
FS_5GSAT_Ph3 overall plan

## Slide 3
General
  TR scope has been set.
  TR architecture and security assumptions have been set.
  There are 2 key issues for Store and Forward Satellite Operation
  There are 38 solutions in the TR.
  All conclusions have been set
Dependencies:
  None
Contentious Issue:
  None
Risks:
  None identified
FS_5GSAT_Ph3 status after SA3#120
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020044 | Study on Security Aspects of 5G Satellite Access Phase 3 | FS_5GSAT_Ph3 | Rel-20 | S3 | February-2025 | 85% | 100% | TR 33.700-29

## Slide 4
Pending issues
  None
Dependencies:
  None
TUs consumed
  5 TUs used by SA3#115, SA3#115Adhoc-e, SA3#116 , SA3#117 , SA3#118 , SA3#119 , SA3#120
TUs remaining
  None
Plan for completion
  None
FS_5GSAT_Ph3 pending work and plan for completion