## Slide 1: SA WG3 Status report for NG_RTC_SEC_Ph2 Work Item on the security support for the Next Generation Real Time Communication services phase 2
Vlasios Tsiatsis, Ericsson
Xiaoting Huang, China Mobile

## Slide 2
6 TUs planned for both the study and the normative work
SA3#122 (May) meeting
  Study
    Was sent for approval in SA#108 plenary
  Normative work
    Normative work for KI#1 “Third party specific identities”: Cat B CR was agreed in SA3#122
    Normative work for Key Issue #2 “Security of IMS based Avatar Communication”: A living document (draft CR) is approved.
    Normative work for KI#3 ”Security and privacy aspects of IMS DC capability exposure”: Cat B CR was agreed in SA3#122
    An LS to SA2/SA4 was sent in SA3#122 (May) requesting clarifications on the IMS avatar communication procedures, KI#2.
SA3#123 (August) meeting
  Normative work
    Normative work for Key Issue #2 “Security of IMS based Avatar Communication”: The living documents/draft CR is expected to be converted to a Cat B CR in this meeting, SA3#123 (August)
Overall plan
NG_RTC_SEC_Ph2 overall plan

## Slide 3
General
  TR 33.790 v1.2.0 contains the scope, assumptions clauses, 3 key issues:
    Key Issue #1: Third party specific identities
      Concluded and included in the WID
    Key Issue #2: Security of IMS based Avatar Communication
      Concluded and included in the WID
    Key Issue #3: Security and privacy aspects of IMS DC capability exposure
      Concluded and included in the WID
  Exception sheet was submitted for the March SA plenary.
  For the normative work for KI#2 an LS to SA2/SA4 was sent in SA3#122 (May) requesting clarifications on the IMS avatar communication procedures. There is a living document/draft CR capturing a large part of the normative work
Dependencies:
  The KI#2 normative work depends on the SA2 normative work mainly in TS 23.228.
Contentious Issue:
  None
Risks:
  Cat F clarification CRs may need to be submitted to the SA3#123/SA3#124 (October/November) meetings due a pending LS reply from SA2/SA4
NG_RTC_SEC_Ph2 status after SA3#122
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020038 | Study on the security support for the Next Generation Real Time Communication services phase 2 | NG_RTC_SEC_Ph2 | Rel-19 | S3 | June- 2025 Sept-2025 | 60% | 80% | TS 33.203, TS 33.328

## Slide 4
Pending issues
  SA2 study dependency
Dependencies:
  The KI#2 normative work depends on the SA2 normative work mainly in TS 23.228. An LS was sent to SA2/SA4 to request clarification on the TS 23.228 IMS avatar communication procedures in order to clarify the authorization aspects of these procedures. However, the normative work is expected to be 80% complete in SA3#123 (August meeting).
TUs consumed
  SA3#115: 0.5 TU
  SA3#115Adhoc-e: 0.5 TU
  SA3#116: 0.5 TU
  SA3#117: 0.5 TU
  SA3#118: 0.5 TU
  SA3#119: 0.5 TU
  SA3#119-Adhoc-e: 0.5 TU
  SA3#120: 0.5 TU
  SA3#121: 0.5 TU
  SA3#122: 0.5 TU
TUs remaining
  SA3#123 (2025): 1.0 TUs for the work item corresponding to the study
Plan for completion
  See earlier slide 2
NG_RTC_SEC_Ph2 pending work and plan for completion