## Slide 1: SA WG3 Status Report for FS_AIoT_Sec
Marcus Wong – OPPO
Longhua Guo - Huawei

## Slide 2
In SA3#115-Adhoc meeting: -
  Get KIs agreed
In SA3#116 meeting -
  Get KIs agreed
  Get solutions agreed
In SA3#117 meeting -
  Get Kis, architecture and assumptions agreed
  Get additional solutions and evaluations agreed
  Get initial conclusion agreed
In SA3#118 meeting -
  Get final solutions agreed
  Get more conclusions agreed
In SA3#119 meeting -
  Solution and conclusion update
FS_AIoT_Sec overall plan
In SA3#119 Ad Hoc meeting -
  Solution and conclusion update
In SA3#120 meeting -
  Solution and conclusion update
In SA3#121 meeting -
  Solution and conclusion update
In SA3#122 meeting -
  Get conclusions Agreed, TR ready for SA plenary approval

## Slide 3
TR 33.713 Summary
FS_AIoT_Sec Status
issue | Topic | Status
Generic part | High-level issue | Conclusion reached
KI#1 | Protection on enable and disable | Conclusion reached. Reusing KI#4 sol
KI#2 | T2 UE reader authorization | Not addressed in Release 19
KI#3 | ID privacy | Conclusion reached. The detailed procedure is to be determined in normative phase
KI#4 | Information protection | Conclusion reached
KI#5 | Authentication | Conclusion reached
KI#6 | Exposure of Inventory Device Quantity | No additional work required in normative phase
KI#7 | Authorization of external AF for Inventory | No additional work required in normative phase
KI#8 | Amplification of resource exhaustion by exploiting AIoT paging messages | No additional work required in normative phase
KI#9 | Attacks on carrier waves | No additional work required in normative phase
WID proposal was approved as in S3-251150 |  | 

## Slide 4
General
  49 contributions from SA3#121 (30 contributions untreated)
  49 contributions from SA3#122
Dependencies:
  Coordination with SA2 on ID privacy
Contentious Issue:
  Details will be discussed during normative phase.
Risks:
  None.
‘FS_AIoT_Sec status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030031 | Security of Ambient IoT services in 5G | FS_AIoT_Sec | Rel-19 | S3 | June-2025 | 75% | 95% | +20%

## Slide 5
Pending issues
  none
Dependencies:
  none
TUs consumed
  SA3#115 AdHoc – 1 TU
  SA3#116 – 2 TU
  SA3#117 – 2 TU
  SA3#118 – 3 TU
  SA3#119 – 2 TU
  SA3#119e – 1 TU
  SA3#120 – 3 TU
  SA3#121 – 1 TU
  SA3#122 – 1 TU
Plan for completion
  N/A
FS_AIoT_Sec pending work and plan for completion