## Slide 1: SA WG3 Status report for FS_AIMLE_SEC
Sheeba Backia Mary B.
Lenovo, Motorola Mobility

## Slide 2
13 – 17 Oct meeting (SA3#124, Wuhan):
  Progressed aspects: 2 Stable Key Issues
17 - 21 Nov Meeting (SA3#125, Dallas):
  Progressed aspects: Solutions to KI#1, 2
9 – 13 Feb Meeting (SA3#126, India):
  Focus to achieve: Solution evaluation and conclusion, Initiate WID.
  Send TR for Info/Approval
13 – 17 April Meeting (SA3#127, Malta):
  Focus to achieve: Initiate Normative
18 – 22 May Meeting (SA3#128, China):
  Focus to achieve: Stabilize Normative
24 – 28 Sept Meeting (SA3#129, Prague):
  Focus to achieve: Finish Normative
FS_AIMLE_SEC Status Over-all Plan
Consumed TUs
  Study: 0.75 TUs
    SA3#124: .25 TU
    SA3#125: .5 TU
Available TUs
  Study: 1.25 TUs
  Normative: 1 TU

## Slide 3
Key Issues | Solutions | Solution status
Key Issue #1: Authorization for AIMLE Service Security for AIML members | Sol #1, #2, #3, #5 | Solution details available. Editor’s Notes to be resolved and evaluation to be done.
Key Issue #2: Secure AIMLE ML Model Access | Sol #3, #4 | Solution details available. Editor’s Notes to be resolved and evaluation to be done.
TR 33.786 Summary
FS_AIMLE_SEC Status

## Slide 4
General
  TR 33.786 v0.3.0 contains the following aspects:
    Security Assumptions
    2 Key Issues
      Key Issue #1: Authorization for AIMLE Service Security for AIML members
      Key Issue #2: Secure AIMLE ML Model Access
    5 Solutions
      Solution #1: Authorization for AIMLE Services
      Solution #2: Authorization of AIMLE clients acting as FL members for access to AIMLE Service Security
      Solution #3: Re-using existing mechanisms
      Solution #4: Authorization for Secure AIMLE based ML Model Access
      Solution #5: FL member authorization for AIMLE services
Dependencies:
  None (the SID has no RAN impacts)
FS_AIMLE_SEC Status
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090016 | Study on AIML Enablement Service Security | FS_AIMLE_SEC | Rel-20 | S3 | Dec 2024 | 30% | 60% | TR 33.786

## Slide 5: FS_AIMLE_SEC Status
  SA2/RAN impacts and dependencies:
  None for RAN & SA2 determined yet.
Contentious Issue:
  No
Focus for the Next Meeting :
  Solution evaluations completion and conclusions.
  If conclusion completion needs additional meeting cycle, then TSG approval need to be extended to SA#112. SID’s current TSG approval is marked as SA#111 in SP-251238. But current TUs are good!
Overall Plan:
  See dedicated slide (No. 2).
Risks:
  None.