## Slide 1: SA WG3 Status report for ‘FS_AIML_CN_Ph2_SEC’
Samir Ferdi (Interdigital)
Xie Zhenhua (vivo)

## Slide 2
TUs planned
In SA3#124 meeting:
  0.5TU - TR skeleton, and new KI#1 and KI#2 and new solutions for KI#1 are approved
In SA3#125 meeting:
  0.5TU - Update to KI#1, new solutions for KI#2, KI#1, and updates to solutions for KI#1 are approved
In SA3#126 (upcoming) meeting:
  Request to be part of the agenda
  Adress pending ENs and add evaluations based on latest TR 23.700-04 K#1 conclusion progress, add interim conclusions
Overall plan
‘FS_AIML_CN_Ph2_SEC’ overall plan
Total TU Estimated | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
3.5 | 2.5 | 1 | Yes | NA

## Slide 3
General
  TR 33.785 v0.3.0 contains 2 key issues and 11 solutions
Dependencies:
  SA2 TR 23.700-04 conclusions
Contentious Issue:
  None identified
Risks:
  None identified
‘FS_AIML_CN_Ph2_SEC’ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090019 | Study on Security for Core Network Enhanced Support for Artificial Intelligence (AI) / Machine Learning (ML) Phase 2 | FS_AIML_CN_Ph2_SEC | Rel-20 | S3 | March-2026 | 20% | 40% | -

## Slide 4
Pending issues
  Resolve solution ENs, add evaluations and conclusions
TUs consumed
  SA3#124 - 0.5TU
  SA3#125 - 0.5TU
TUs remaining
  2.5 TU
TUs to be requested for the upcoming meeting
  0.5 TUs
Plan for completion
  TR for information and approval for SA#112
‘FS_AIML_CN_Ph2_SEC’ pending work and plan for completion