## Slide 1: SA WG3 Status report for ‘FS_NR_Femto_SEC_Ph2’
Peilin Liu (ZTE)

## Slide 2
TUs planned
In SA3#124 meeting:
  0.5TU - TR skeleton, assumptions and new KIs, new solutions are approved
In SA3#125 meeting:
  0.25TU - Evaluations, new solutions and KI updates are approved
In SA3#126 (upcoming) meeting:
  Request to be part of the agenda - 0.5TU
  New solutions, solution updates and evaluations, discussion on conclusions
Overall plan
‘FS_NR_Femto_SEC_Ph2’ overall plan
Total TU Estimated | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
3 | 2 | 1 | Maybe | NA

## Slide 3
General
  TR 33.746 v0.3.0 contains 5 key issues and 6 solutions
Dependencies:
  None identified
Contentious Issue:
  None identified
Risks:
  None identified
‘FS_NR_Femto_SEC_Ph2’ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090030 | New SID on Security Aspect for NR Femto Phase 2 | FS_NR_Femto_SEC_Ph2 | Rel-20 | S3 | March-2026 | 20% | 40% | -

## Slide 4
Pending issues
  Solutions to existing KIs
  EN resolve and evaluations to solutions
TUs consumed
  SA3#124 - 0.5TU
  SA3#125 - 0.25TU
TUs remaining
  2.25 TU
TUs to be requested for the upcoming meeting
  0.5 TUs
Plan for completion
  SA#112 send TR for information and approval
‘FS_NR_Femto_SEC_Ph2’ pending work and plan for completion