## Slide 1: SA WG3 Status report for ‘FS_5GSAT_Ph4_SEC’
Hongil Kim (Qualcomm)
Zhou Wei (CATT)

## Slide 2
TUs planned
In SA3#124 meeting:
  A key issue and solutions were agreed
In SA3#125 meeting:
  Solution updates and evaluations were agreed
In SA3#126 (upcoming) meeting:
  Continue to discuss new solutions, solution updates and evaluations
In SA3#127 (upcoming) meeting:
  Finalize solution evaluations
  Discuss preliminary conclusions
In SA3#128 (upcoming) meeting:
  Finalize conclusions and complete the study
Overall plan
‘FS_5GSAT_Ph4_SEC’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
WT1 | 2 | 1 | Maybe | NA

## Slide 3
General
  TR 33.700-30 v0.2.0 currently includes one key issue and 8 solutions in the study.
Dependencies:
  Coordination with SA2/RAN may be needed for architectural and procedural impacts during conclusion phase of the study
Contentious Issues:
  None
Risks:
  None
‘‘FS_5GSAT_Ph4_SEC‘‘ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090022 | Study on Security Aspects of Satellite Access in 5G Phase 4 | ‘FS_5GSAT_Ph4_SEC’ | Rel-20 | S3 | Jun., 2026 | 0% | 50% | -

## Slide 4
Pending issues
  Solution evaluations
  Conclusion
Dependencies:
  Maybe SA2/RAN depending on the conclusion of the study
TUs consumed
  SA3#124 - 0.5 TU
  SA3#125 - 0.5 TU
TUs remaining
  2 TUs
TUs to be requested for the upcoming meeting
  0.5 TU
Plan for completion
  Planned to close the study by SA3#128
‘‘FS_5GSAT_Ph4_SEC‘‘ pending work and plan for completion