## Slide 1: SA WG3 Status report for ‘FS_5G_WAB_SEC’
Weihan Gao(China Telecom)

## Slide 2
TUs planned
In SA3#124 meeting:
  0.5TU-TR skeleton, assumptions and new KIs,1 solution are agreed
In SA3#125 meeting:
  0.5TU- KI updates
In SA3#126 (upcoming) meeting:
  Request to be part of the agenda
  Open for Key issue proposals.
Overall plan
‘FS_5G_WAB_SEC’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
WT1 | 1 | 0.5 | Maybe | RAN3
WT2 | 1 | 0.5 | No | 

## Slide 3
General
  TR 33.724 v0.2.0 contains 4 key issues and 1 solution.
Dependencies:
  None
Contentious Issues:
  None
Risks:
  None
‘‘FS_5G_WAB_SEC‘‘ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090045 | New SID on Security aspects of WAB nodes for NR | ‘FS_5G_WAB_SEC’ | Rel-20 | S3 | May-2026 | 20% | 25% | -

## Slide 4
Pending issues
  Solutions to existing KIs
Dependencies:
  None
TUs consumed
  SA3#124 - 0.5 TU
  SA3#125 – 0.5TU
TUs remaining
  2 TUs
TUs to be requested for the upcoming meeting
  0.25 TUs
Plan for completion
  Planned to close the study by SA3#128
  SA#112 send TR for information and approval
‘‘FS_5G_WAB_SEC‘‘ pending work and plan for completion