## Slide 1: SA WG3 Status report for ‘FS_6G_SEC’
Todor Gamishev (ORANGE)
Suresh Nair (Nokia)

## Slide 2
TUs planned
  50
In SA3#124 meeting:
  Approve skeletton and 3 security areas
In SA3#125 meeting:
  Approve new security areas and start discussion on MAC CE security
In SA3#126 (upcoming) meeting:
  RAN Security area KIs and MAC CE risk analysis
  Attacker model
  New security areas
  Start discussion on Kis in other security areas (if time allows)
Milestones
See S3-253663 and S3-254563 for more details on current workplan and milestones
Overall plan
FS_6G_SEC overall plan

## Slide 3
General
  Sending the TS for information to SA#114. Approval is expected at SA#116
Progress:
  6 Security areas (Security Architecture, RAN Security, UE to Core Network Security, Core Network Security, Subscription Authentication and Authorization, Exposure security) agreed . Annexes on 1)Attacker model, 2)Risk analysis of MAC-CE agreed.
  Key Issue definitions yet to start.
Dependencies:
  RAN impact to be covered by RAN WGs.
  Architecture impact to be covered by SA2.
  Multimedia and codecs aspects to be covered by SA4.
  Charging and OAM impact to be covered by SA5.
  Application enabler related aspects to be covered by SA6
Contentious Issue:
  None
Risks:
  None identified
FS_6G_SEC status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090044 | Study on Security for the 6G System | FS_6G_SEC | Rel-20 | S3 | Jun 2027 | 0 | 4 | TS 33.801-01

## Slide 4
Pending issues
  MAC CE risk analysis: methodology and preparation for joint meeting with RAN2 after SA3#126
  Attacker model methodology
  Some security areas need more progress in SA2 before being defined (such as AI and Data Framework)
TUs consumed
  SA3#124 – 2
  SA3#125 - 2
TUs remaining
  SA3#126 - 46
Plan for completion
  TSG#116
FS_6G_SEC pending work and plan for completion