## Slide 1: SA WG3 Status report for ‘FS_AEAD’
Yuto Nakano (KDDI)
Hu Li (vivo)

## Slide 2
TUs planned
In SA3#124 meeting:
  pCRs agreed on scope, key issues and annex.
In SA3#125 meeting:
  pCRs agreed on key issues and solutions
In SA3#126 (upcoming) meeting:
  Key issue proposals (if any)
  Solutions and evaluations
Overall plan
‘FS_AEAD’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
WT1 | 5 | 0 | Mayby | NA

## Slide 3
General
  TR 33.771 v0.2.0 currently includes scope, 3 key issues and 11 solutions.
Dependencies:
  The conclusion may have NAS impact (CT1) and AS impact (RAN2)
Contentious Issues:
  None
Risks:
  None identified
‘‘FS_AEAD‘‘ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090028 | Study on supporting AEAD algorithms | ‘FS_AEAD’ | Rel-20 | S3 | Sept-2026 | 0% | 20% | -

## Slide 4
Pending issues
  None
Dependencies:
  The conclusion may have NAS impact (CT1) and AS impact (RAN2)
TUs consumed
  SA3#124 - 0.5 TU
  SA3#125 – 1 TU
TUs remaining
  3.5 TUs
TUs to be requested for the upcoming meeting
  1 TU
Plan for completion
  KI updates, new KIs (if any), solution and evaluation for SA3#126
  Solution, evaluation and conclusion for SA3#127
  Evaluation and conclusion for SA3#128
  Planned to close the study by SA3#129
‘‘FS_AEAD‘‘ pending work and plan for completion