## Slide 1: SA WG3 Status Report for ‘FS_AIoT_SEC_Ph2’
Lihui Xiong (OPPO)
Longhua Guo (Huawei)

## Slide 2
TUs planned
  7.5 TUs (total)
In SA3#124 meeting: -
  Get KIs agreed
In SA3#125 meeting -
  Get KIs agreed
  Get solutions agreed
In SA3#126 meeting -
  Update to KIs
  Additional solutions and update evaluations
  Get initial conclusion agreed
‘FS_AIoT_SEC_Ph2’ overall plan
In SA3#127 meeting -
  Get final solutions agreed
  Get more conclusions agreed
  Initial discussion on WID proposal
In SA3#128 meeting -
  Get conclusions agreed, TR ready for SA plenary approval
  WID proposal agreed

## Slide 3
General
  20 contributions from SA3#124
  32 contributions from SA3#125
Dependencies:
  SA2 on stable architecture and conclusions, e.g., whether there will be the registration-like procedure for DO-A capable devices.
  RAN on architecture and protocol stack, e.g., which type(s) of AIoT device supports Topology 2.
Contentious Issue:
  Solution detail requires more discussion.
Risks:
  SA3 requires input from other WGs (e.g., SA2) for R20 AIoT scope alignment and security design. If late conclusion from other WGs, the security work will be lack of time to discuss.
‘FS_AIoT_SEC_Ph2’ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090025 | Study on security aspects of ambient IoT services phase 2 | ‘FS_AIoT_SEC_Ph2’ | Rel-20 | S3 | Jun-2025 | 0% | 30% | +30%

## Slide 4
Pending issues
  Detailed solutions for agreed key issues.
Dependencies:
  SA2 on stable architecture and conclusions, e.g., whether there will be the registration-like procedure for DO-A capable devices.
  RAN on architecture and protocol stack, e.g., which type(s) of AIoT device supports Topology 2.
TUs consumed
  SA3#124 – 0.5 TU
  SA3#125 – 1 TU
TUs remaining
  6 TUs
TUs to be requested for the upcoming meeting
  2 TUs
Plan for completion
  Planned to close the study by SA3#128
FS_AIoT_SEC_Ph2 pending work and plan for completion